## SRR
“Systems Engineering for Mission Success”
|  | System Requirements Review | [6 empty] | Name of the program being reviewed / date
Program Risk Assessment Checklist (27 September 2010)
OVERVIEW: Although the checklist can be printed and completed as a "hard copy", it is designed to be completed electronically as an Excel spreadsheet. When viewed electronically, the small number buttons in the upper left corner of the screen are used to select the level of indenture for the questions in the checklist. A left mouse click on a number button will expand or collapse the entire checklist to the desired level. A left click on the "+" symbol in the left margin of the spreadsheet will expand the level of indenture for that section. A left click on the "-" symbol in the left margin of the spreadsheet will collapse the level of indenture for that section. The buttons in Row 11 run specific macros. The buttons in Column A allow a user to designate and sort specific questions as "Special Interest" (i.e., High Priority, Flagged, Question). The colored buttons in Row 11, Column C allow the user to sort questions by Technical Discipline, to provide a Level 1 roll-up of the risk characters assigned, or to hide specific information. For example selecting the "Logistics" button results in the display of all Level 1 Logistics-related questions and assigned information. All other questions will be hidden. COMPLETING THE CHECKLIST: 1. In the upper right corner of the checklist, enter the name of the program being reviewed, the date(s) of the review, along with the name, code and technical specialty of the person(s) completing the checklist. 2. A "Risk Character" (i.e., R / Y / G / U / NA) should be assigned for each question by direct entry or left clicking in each box to activate the "drop down" menu. The assigned Risk Characters will automatically total and display in the Level 1 (and Level 2, as applicable) row(s). Selection of a summary tab (Excel "Sheet") at the bottom of the checklist will provide a summary of all questions assigned a particular risk character (e.g., selecting the RED tab will display all questions assigned a RED risk character). To delete a "Risk Character" from a box, click in the box and press the "Delete" button on the keyboard. 3. Any question requiring further attention (Special Interest) should be similarly marked in Column A as "High Priority", "Flagged", or "Question" to facilitate follow-up. 4. Narrative, amplifying, and / or mitigation information should be entered in the "Comments Mitigation" box (Column J) at the right of each question.
Name / Code / Technical Specialty of reviewer
SAVING THE CHECKLIST: Save the completed checklist in a new file with a unique name such as "UAV SRR 9May07ajo".
|  |  | Risk Character | [6 empty] | High Priority
[8 empty] | R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable |  | Flagged
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigation | Question
| Level 1, logistics, PQM, T&E, software, risk, EVM, training, HSI, technology, programmatic, interoperability | 1. Timing / Entry Criteria | 0 | 0 | 0 | 0 | 0 | 1
| programmatic | a. Has an Alternative Systems Review (ASR) been successfully completed? | [5 empty] | 1.a
| logistics, T&E, software, risk, PQM, EVM, training, HSI, technology, programmatic, interoperability | b. Is the program ready to conduct System Requirements Review (SRR) based upon satisfying SRR entry criteria vice a pre-determined schedule date? | [5 empty] | 1.b
| logistics, T&E, software, risk, PQM, EVM, training, HSI, technology, programmatic, interoperability | c. Have all prior technical review Requests for Action (RFAs) been properly dispositioned, and closed? | [5 empty] | 1.c
| logistics, programmatic | d. Have all prior logistics review RFAs been properly dispositioned, and closed? | [5 empty] | 1.d
| software, risk, programmatic | e. Is the program using an effective Integrated Data Environment (IDE) to store data? | [5 empty] | 1.e
| Level 1, logistics, PQM, T&E, software, risk, EVM, training, HSI, technology, programmatic, interoperability | 2. Planning | 0 | 0 | 0 | 0 | 0 | 2
| programmatic | a. Was a Systems Engineering (SE) knowledgeable chairperson assigned? | [5 empty] | 2.a
| logistics, T&E, software, risk, PQM, EVM, training, HSI, technology, programmatic, interoperability | b. Has a Systems Engineering Plan (SEP) been developed and implemented? | [5 empty] | 2.b
| logistics, T&E, software, risk, PQM, EVM, training, HSI, technology, programmatic, interoperability | c. Is the technical review board properly staffed, and did the appropriate technical disciplines participate in the review? | [5 empty] | 2.c
| logistics, programmatic | d. Was a Manpower Estimate Report (MER) completed and approved? | [5 empty] | 2.d
| software, T&E, technology, risk, logistics, programmatic, interoperability | e. Have the Key Performance Parameters (KPPs) and other performance requirements, both specified and derived been defined, quantified and documented? | [5 empty] | 2.e
| T&E, risk, programmatic, interoperability | f. Has the system Net-Ready Key Performance Parameter (NR-KPP) been approved? | [5 empty] | 2.f
| risk, PQM, software, programmatic, interoperability | g. Information Support Plan (ISP) | 0 | 0 | 0 | 0 | 0 | 2.g
| risk, PQM, software, programmatic, interoperability | (1) Has the system ISP been approved? | [5 empty] | 2.g(1)
| risk, PQM, software, programmatic, interoperability | (2) Are the architecture products developed for the ISP Core Architecture Data Model (CADM) compliant? | [5 empty] | 2.g(2)
| risk, PQM, software, programmatic, interoperability | (3) Have the architecture products been delivered? | [5 empty] | 2.g(3)
| training, logistics, programmatic | h. Will fielding the system require changes to Doctrine, Organization, Training, Materiel, Leadership and Education, Personnel and Facilities (DOTMLPF) solutions in order to advance joint warfighting capabilities? | [5 empty] | 2.h
| logistics, risk, T&E, software, programmatic, interoperability | i. Is Operational Availability (Ao) a KPP, or has a waiver been submitted or obtained? | [5 empty] | 2.i
| programmatic | j. Was the acquisition strategy developed and documented? | [5 empty] | 2.j
| T&E, programmatic | k. Is there an approved Test and Evaluation (T&E) Strategy? | [5 empty] | 2.k
| risk, T&E, software, programmatic, interoperability | l. Will System of Systems (SoS) / Family of Systems (FoS) testing be required? | [5 empty] | 2.l
| T&E, risk, software, programmatic | m. Is system certification required, and have all certifying organizations been involved in identifying certification requirements? | [5 empty] | 2.m
| HSI, T&E, programmatic | n. Does the contract specification contain performance requirements to satisfy Human Systems Integration (HSI) requirements for each domain addressed in the Capability Development Document (CDD), including minimum performance requirements for those domains not specifically addressed in the CDD? | [5 empty] | 2.n
| risk, software, programmatic | o. SRR Metrics | 0 | 0 | 0 | 0 | 0 | 2.o
| software, programmatic | (1) Are software metrics being developed? | [5 empty] | 2.o(1)
| software, programmatic | (2) Do the requirements metrics show progress, quality, and volatility actuals as compared to the Software Development Plan (SDP)? | [5 empty] | 2.o(2)
| software, programmatic | (3) Does the staff metric show a planned staffing level consistent with the software program budget and schedule? | [5 empty] | 2.o(3)
| risk, software, programmatic | (4) Do the other metrics (i.e., size, quality, cost, schedule, etc.) show plans consistent with successful execution of the software program? | [5 empty] | 2.o(4)
| T&E, HSI, software, logistics, risk, programmatic, interoperability | p. T&E Planning | 0 | 0 | 0 | 0 | 0 | 2.p
| T&E, programmatic | (1) Is the T&E strategy current? | [5 empty] | 2.p(1)
| T&E, programmatic, interoperability | (2) Are operating agreements (Memorandum of Agreement (MOAs) / Memorandum of Understanding (MOUs)) in place? | [5 empty] | 2.p(2)
| T&E, programmatic, interoperability | (3) Does planning reflect Integrated Test Team (ITT) organization and testing (contractor / Developmental Test (DT) / Operational Test (OT))? | [5 empty] | 2.p(3)
| T&E, HSI, software, logistics, risk, programmatic, interoperability | (4) Has the Test and Evaluation Master Plan (TEMP) been developed? | [5 empty] | 2.p(4)
| T&E, programmatic | (a) Have all test organizations accepted the TEMP development? | [5 empty] | 2.p(4)(a)
| T&E, programmatic | (b) Does projected TEMP approval date support acquisition milestone? | [5 empty] | 2.p(4)(b)
| T&E, software, programmatic | (c) Are all test events traceable from system requirements (Initial Capabilities Document (ICD) / CDD) to the specification to the TEMP? | [5 empty] | 2.p(4)(c)
| T&E, risk, software, programmatic, interoperability | (d) Does the TEMP clearly address all KPPs? | [5 empty] | 2.p(4)(d)
| T&E, programmatic | (e) Do the DT and OT test events in the TEMP reflect planned system maturity? | [5 empty] | 2.p(4)(e)
| T&E, logistics, risk, software programmatic, interoperability | (5) Have facilities / test resources (Government and contractor) been defined and included in the planning? | [5 empty] | 2.p(5)
| risk, software, T&E, logistics, programmatic, interoperability | (6) Are there sufficient test assets (e.g. test aircraft, ground test articles, System Integration Laboratory (SILs)) to conduct the planned test program? | [5 empty] | 2.p(6)
| T&E, logistics, programmatic | (7) Are resource providers (facilities / people / equipment) included in test planning? | [5 empty] | 2.p(7)
| T&E, programmatic | (8) Is there user acceptance of the test planning, and are there provisions for user participation? | [5 empty] | 2.p(8)
| PQM, risk, T&E | q. Quality Planning | 0 | 0 | 0 | 0 | 0 | 2.q
| PQM, risk | (1) Has the organization established, documented, implemented, maintained and continually improved a quality management system in accordance with the applicable standard (i.e., ISO 9001, AS 9100, etc.)? | [5 empty] | 2.q(1)
| PQM, risk | (2) Does the organization have an established and maintained quality program plan? | [5 empty] | 2.q(2)
| PQM, risk, T&E | (3) Does the manufacturing plan identify and make provision for special controls, processes, test equipment, fixtures, tooling and skills for (1) assuring the quality of the product as a whole as well as its parts and (2) maintaining schedule as a function of quantity? | [5 empty] | 2.q(3)
| PQM | (4) Is the quality staff trained to support the unique requirements of the program? | [5 empty] | 2.q(4)
| PQM | (5) Have the qualification and certification requirements been identified for key quality positions and personnel? | [5 empty] | 2.q(5)
| PQM | (6) Is a qualification and certification training program in effect? | [5 empty] | 2.q(6)
| Level 1, logistics, PQM, T&E, software, risk, EVM, training, HSI, technology, programmatic, interoperability | 3. Program Schedule | 0 | 0 | 0 | 0 | 0 | 3
| risk, programmatic | a. Is the schedule reflective of available resources? | [5 empty] | 3.a
| T&E, risk, programmatic | b. Is there adequate time allotted in the program's schedule for T&E? | [5 empty] | 3.b
| T&E, risk, programmatic | c. Will Early Operational Assessments (EOAs) / Operational Assessments (OAs) be conducted in the test program? | [5 empty] | 3.c
| programmatic | d. Does the program schedule have an identified critical path? | [5 empty] | 3.d
| risk, technology, programmatic | e. Is the critical path consistent with overall technical risk, and are the critical path tasks based upon the preferred system concept and system specification? | [5 empty] | 3.e
| T&E, EVM, risk, logistics, PQM, training, software, technology, HSI, programmatic, interoperability | f. Critical Path Impacts | 0 | 0 | 0 | 0 | 0 | 3.f
| T&E, EVM, risk, logistics, PQM, training, software, technology, HSI, programmatic, interoperability | (1) What is the program status versus the critical path? | [5 empty] | 3.f(1)
| risk, T&E, software, programmatic | (2) Are system and software critical path drivers being tracked? | [5 empty] | 3.f(2)
| T&E, risk, software, programmatic, interoperability | g. Is this system on the critical path for delivery of a SoS / FoS capability? | [5 empty] | 3.g
| T&E, risk, software, programmatic | h. Is there adequate time allotted in the program schedule for software design, implementation, and testing (unit, integrated units, system integration, regression, etc.) based on the latest revised software estimates? | [5 empty] | 3.h
| Level 1, logistics, PQM, T&E, software, risk, EVM, training, HSI, technology, programmatic, interoperability | 4. Management Metrics | 0 | 0 | 0 | 0 | 0 | 4
| technology, logistics, risk, software, T&E, programmatic, interoperability | a. Status versus Plan for Cost / Schedule / Performance / KPP | 0 | 0 | 0 | 0 | 0 | 4.a
| logistics, T&E, software, risk, technology, programmatic, interoperability | (1) Is the latest revised estimate of each KPP in accordance with the Acquisition Program Baseline (APB)? | [5 empty] | 4.a(1)
| logistics, T&E, software, risk, technology, programmatic, interoperability | (2) Is the KPP planning reflective of program risks and technical results? | [5 empty] | 4.a(2)
| T&E, risk, software, programmatic, logistics, HSI | b. Has the Cost Analysis Requirements Description (CARD) been developed, and is it consistent with the system specification and latest estimates of costs? | [5 empty] | 4.b
| risk, T&E, logistics, programmatic | c. Does the CARD reflect the planned test program? | [5 empty] | 4.c
| T&E, EVM, PQM, logistics, risk, training, software, HSI, technology, programmatic, interoperability | d. Is the latest estimate of development costs consistent with the technical risk of the program, the program's critical path plan, and available resources? | [5 empty] | 4.d
| risk, logistics, software, T&E, programmatic | e. Are the software and T&E tasks in the program adequately funded based on latest cost estimate? | [5 empty] | 4.e
| EVM, risk, logistics, programmatic | f. Earned Value Management (EVM) | 0 | 0 | 0 | 0 | 0 | 4.f
| EVM, risk, logistics, programmatic | (1) Are the EVM data up to date? | [5 empty] | 4.f(1)
| EVM, risk, logistics, programmatic | (2) Is the EVM baseline being used as a program execution tool (i.e. by management and at the working level)? | [5 empty] | 4.f(2)
| EVM, risk, logistics, programmatic | (3) Are the work packages based on earned value vice level of effort? | [5 empty] | 4.f(3)
| EVM, risk, logistics, programmatic | (4) Are the EVM data consistent with known technical risks and challenges in the program? | [5 empty] | 4.f(4)
| EVM, risk, logistics, programmatic | (5) Are the EVM data being used to adjust program resources to address risk issues? | [5 empty] | 4.f(5)
| risk, T&E, PQM, software, EVM, technology, HSI, training, logistics, programmatic, interoperability | g. Is the Work Breakdown Structure (WBS) consistent with the cost account structure and the program plan / SEP? | [5 empty] | 4.g
| software, risk, programmatic | h. Management Costs | 0 | 0 | 0 | 0 | 0 | 4.h
| software, risk, programmatic | (1) Are software cost metrics, particularly cost based on sizing and staff, known for each software element of the system concept? | [5 empty] | 4.h(1)
| technology, software, risk, programmatic | (2) Are the costs for Commercial Off-The-Shelf (COTS) / Government Off-The-Shelf (GOTS) / Non-developmental Item (NDI) known, and are they realistic? | [5 empty] | 4.h(2)
| Level 1, logistics, PQM, T&E, software, risk, EVM, training, HSI, technology, programmatic, interoperability | 5. Program Staffing | 0 | 0 | 0 | 0 | 0 | 5
| HSI, PQM, T&E, logistics, risk, technology, EVM, training, software, programmatic, interoperability | a. Is there a complete organization structure shown, and is the organization consistent with the technical challenges / risks of the program? | [5 empty] | 5.a
| HSI, PQM, T&E, logistics, risk, technology, EVM, training, software, programmatic, interoperability | b. Are key Government / contractor interfaces identified, and are these consistent with program risks? | [5 empty] | 5.b
| HSI, PQM, logistics, programmatic, interoperability | c. Is the Supportability Integrated Product Team (SIPT) adequately staffed with representatives from appropriate functional disciplines? | [5 empty] | 5.c
| T&E, logistics, risk, HSI, PQM, technology, EVM, training, software, programmatic, interoperability | d. Staffing Impacts | 0 | 0 | 0 | 0 | 0 | 5.d
| T&E, logistics, risk, HSI, PQM, technology, EVM, training, software, programmatic, interoperability | (1) Is adequate Government and contractor staffing (expertise and quantity) available to execute the schedule? | [5 empty] | 5.d(1)
| software, risk, programmatic | (2) Is the software staff planned for this program consistent with the amount of software to be developed and tested and the level of expertise needed to develop this type of software, and is there adequate staff available to support the schedule? | [5 empty] | 5.d(2)
| T&E, logistics, risk, HSI, PQM, technology, EVM, training, software, programmatic, interoperability | e. Are key interfaces with joint programs established, and are they represented at the review? | [5 empty] | 5.e
| T&E, software, logistics, risk, technology, programmatic, interoperability | f. Is there a single point of contact within the program for all Net-Centric interoperability issues? | [5 empty] | 5.f
| T&E, risk, programmatic | g. Is there confidence that all required flight clearance performance monitors are involved and concur with the system requirements? | [5 empty] | 5.g
| T&E, logistics, training, risk, programmatic | h. T&E Staffing | 0 | 0 | 0 | 0 | 0 | 5.h
| T&E, risk, logistics, programmatic | (1) Is T&E staffing sufficient? | [5 empty] | 5.h(1)
| T&E, risk, training, programmatic | (2) Is there an assigned T&E Integrated Product Team (IPT) lead with the appropriate career field training? | [5 empty] | 5.h(2)
| T&E, programmatic | (3) Does the program have an assigned DT representative? | [5 empty] | 5.h(3)
| T&E, programmatic | (4) Does the program have an assigned OT representative? | [5 empty] | 5.h(4)
| risk, T&E, logistics, programmatic | (5) Are current and future T&E staffing plans developed and adequately funded? | [5 empty] | 5.h(5)
| PQM, risk | i. Quality Staffing | 0 | 0 | 0 | 0 | 0 | 5.i
| PQM, risk | (1) Do the personnel performing quality functions have sufficient authority, responsibility and freedom of action to identify and evaluate quality problems and initiate solutions? | [5 empty] | 5.i(1)
| PQM, risk | (2) Does the program identify the organizational element responsible for each of the various quality efforts, and are they appropriate to accomplish their functions? | [5 empty] | 5.i(2)
| Level 1, logistics, PQM, T&E, software, risk, EVM, training, HSI, technology, programmatic, interoperability | 6. Process Review | 0 | 0 | 0 | 0 | 0 | 6
| logistics, T&E, PQM, risk, EVM, training, software, programmatic, interoperability, HSI, technology | a. Program Management Processes | 0 | 0 | 0 | 0 | 0 | 6.a
| programmatic, technology, risk | (1) Are the program management processes adequate to address the technical challenges of the program, and adequate to address program risks? | [5 empty] | 6.a(1)
| programmatic, technology, risk | (2) Is there an updated program management plan that is reflective of the emergent technical issues and risks? | [5 empty] | 6.a(2)
| risk, technology, programmatic | (3) Are there program management processes in place to properly manage the system requirements and attendant technical emphasis areas? | [5 empty] | 6.a(3)
| logistics, T&E, PQM, risk, EVM, training, software, HSI, technology, programmatic, interoperability | (4) Is the program being managed to adjust resources, and to address issues? | [5 empty] | 6.a(4)
| logistics, T&E, PQM, risk, EVM, training, software, HSI, technology, programmatic, interoperability | b. Systems Engineering (SE) Processes | 0 | 0 | 0 | 0 | 0 | 6.b
| logistics, T&E, PQM, risk, EVM, training, software, HSI, technology, programmatic, interoperability | (1) Is there a defined SE process? | [5 empty] | 6.b(1)
| logistics, T&E, PQM, risk, EVM, training, software, HSI, technology, programmatic, interoperability | (2) Are the processes shared by the Government and contractor (if applicable) team? | [5 empty] | 6.b(2)
| logistics, T&E, PQM, risk, EVM, training, software, HSI, technology, programmatic, interoperability | (3) Are the planned technical reviews scheduled and event driven verses schedule driven, and is the technical review strategy described in the SEP? | [5 empty] | 6.b(3)
| logistics, T&E, PQM, risk, EVM, training, software, HSI, technology, programmatic, interoperability | (4) Are the SE processes adequate to support the technical requirements of the technical reviews, and are the technical teams working against a defined technical baseline? | [5 empty] | 6.b(4)
| technology, risk, logistics, T&E, programmatic | (5) Is the Supportability Analysis Plan (SAP) part of the SEP? | [5 empty] | 6.b(5)
| technology, risk, logistics, T&E, programmatic | (6) Is the System Operational Effectiveness (SOE) model described in the SEP? | [5 empty] | 6.b(6)
| HSI, logistics, programmatic | (7) Is there an HSI IPT and / or an active HSI working group (to include program management, logistics, engineering, other) assigned for this program? | [5 empty] | 6.b(7)
| risk, HSI, logistics, programmatic | (8) Is there a comprehensive HSI plan or equivalent, in accordance with Department of Defense (DoD) 5000.2 to optimize total system performance? | [5 empty] | 6.b(8)
| risk, HSI, logistics, programmatic | (9) Will funding be sufficient to allow all aspects of the HSI plan to be implemented in this phase and any future acquisition phase for this program? | [5 empty] | 6.b(9)
| T&E, risk, logistics, HSI, programmatic | (10) Is HSI included in the Statement of Work (SOW), Contract Data Requirements List(s) (CDRLs), Contract Line Item Number(s) (CLINs)? | [5 empty] | 6.b(10)
| HSI, T&E, logistics, risk, programmatic | (11) Is there an Electromagnetic Environmental Effects (E3) IPT and / or active E3 working group or Electromagnetic Compatibility Assessment Board (EMCAB) assigned for this program? | [5 empty] | 6.b(11)
| PQM, EVM, HSI, logistics, training, risk, technology, T&E, software, programmatic, interoperability | c. Risk Management (RM) Processes | 0 | 0 | 0 | 0 | 0 | 6.c
| risk, programmatic | (1) Is there a defined risk management process, and is the Risk Management Plan (RMP) up to date and being used? | [5 empty] | 6.c(1)
| risk, programmatic | (2) Is the RM process shared by the Government and contractor team? | [5 empty] | 6.c(2)
| risk, programmatic | (3) Does the risk management process properly track all risks on a continuous basis, and provide for update of the mitigation approaches? | [5 empty] | 6.c(3)
| risk, programmatic | (4) How are risks associated with SoS / FoS requirements and risks external to the program being mitigated using the RM process? | [5 empty] | 6.c(4)
| T&E, risk, programmatic | (5) Are T&E members utilizing the program risk management system? | [5 empty] | 6.c(5)
| risk, programmatic | (6) Are mitigation approaches in place for all “yellow” and “red” risks, and are risk mitigations resourced? | [5 empty] | 6.c(6)
| PQM, EVM, HSI, logistics, training, risk, technology, T&E, software, programmatic, interoperability | (7) Does the risk management process provide for risk updates to support the technical reviews and program management (acquisition) reviews? | [5 empty] | 6.c(7)
| PQM, EVM, HSI, logistics, training, risk, technology, T&E, software, programmatic, interoperability | d. Test Processes | 0 | 0 | 0 | 0 | 0 | 6.d
| PQM, EVM, HSI, logistics, training, risk, technology, T&E, software, programmatic, interoperability | (1) Does the TEMP address SoS / FoS test and certification requirements? | [5 empty] | 6.d(1)
| T&E, risk, logistics, software, HSI, programmatic | (2) Are support related performance and acceptance criteria developed for demonstration during planned testing and / or modeling and simulation? | [5 empty] | 6.d(2)
| HSI, T&E, logistics, programmatic | (3) Are logistics parameters and tests included in the TEMP? | [5 empty] | 6.d(3)
| T&E, HSI, logistics, programmatic | (4) Has the Ao portion of test plans been defined or updated for this phase of the program? | [5 empty] | 6.d(4)
| T&E, HSI, PQM | (5) Are T&E personnel involved in the requirements development to ensure testability? | [5 empty] | 6.d(5)
| HSI, T&E, logistics, programmatic | (6) Are HSI metrics incorporated into the program's T&E activities? | [5 empty] | 6.d(6)
| T&E, risk, technology, programmatic, interoperability | (7) Is the interoperability KPP testing planned and resources identified? | [5 empty] | 6.d(7)
| software, T&E, programmatic | (8) Have appropriate modeling and simulation tools been identified? | [5 empty] | 6.d(8)
| T&E, logistics, programmatic | (9) Has contractor submitted a detailed T&E strategy as part of contract deliverables? | [5 empty] | 6.d(9)
| software, risk, programmatic | e. Has the program team accessed and applied knowledge management lessons learned? | [5 empty] | 6.e
| HSI, PQM, risk, EVM, software, logistics, training, technology, T&E, programmatic, interoperability | f. Does the program acquisition strategy include full life cycle support planning, and address actions to assure sustainment and continuous improvement of product affordability? | [5 empty] | 6.f
| software, risk, programmatic | g. Software | 0 | 0 | 0 | 0 | 0 | 6.g
| software, risk, programmatic | (1) Is the SDP up to date and is it being used? | [5 empty] | 6.g(1)
| software, risk, programmatic | (2) Is the software engineering environment fully defined and planned to be in place when needed? | [5 empty] | 6.g(2)
| software, programmatic | (3) Are there tools in place to support development of designs that accurately reflect the system and functional requirements, and will they support traceability in both directions? | [5 empty] | 6.g(3)
| software, programmatic | (4) Are the functional requirements baselined to support software preliminary design? | [5 empty] | 6.g(4)
| Level 1, software, T&E, EVM, logistics, risk, PQM, training, programmatic, HSI, technology, interoperability | 7. Product Support | 0 | 0 | 0 | 0 | 0 | 7
| HSI, PQM, T&E, software, training, logistics, EVM, technology, risk, programmatic, interoperability | a. Life Cycle Logistics | 0 | 0 | 0 | 0 | 0 | 7.a
| HSI, PQM, T&E, software, training, logistics, EVM, technology, risk, programmatic, interoperability | (1) Key Logistics Considerations | [5 empty] | 7.a(1)
| logistics, risk, programmatic | (a) Has the impact of the proposed system on the planned maintenance capabilities been assessed for the period the system will be introduced? | [5 empty] | 7.a(1)(a)
| risk, HSI, logistics, programmatic | (b) Have preliminary manpower and personnel requirements and constraints been assessed for quantity, skill levels, and use of contractor support? | [5 empty] | 7.a(1)(b)
| HSI, risk, logistics, programmatic | (c) Has compilation of information and requirements for logistics footprint reductions, deployment requirements, and other factors affecting the in-theater operational concept begun? | [5 empty] | 7.a(1)(c)
| T&E, risk, logistics, HSI, programmatic | (d) Has the development of operating and support reliability objectives and their corresponding benefits and resource requirements been initiated? | [5 empty] | 7.a(1)(d)
| T&E, risk, logistics, HSI, programmatic | (e) Have the performance histories of prior systems or systems of similar capability been considered? | [5 empty] | 7.a(1)(e)
| HSI, PQM, T&E, software, training, logistics, EVM, technology, risk, programmatic, interoperability | (f) Have the compilation and assessment of data on the projected sustainment demand, standardization of platforms, and required support equipment been initiated? | [5 empty] | 7.a(1)(f)
| HSI, PQM, T&E, software, training, logistics, EVM, technology, risk, programmatic, interoperability | (2) Key Logistics Information | [5 empty] | 7.a(2)
| HSI, T&E, logistics, programmatic | (a) Have key performance and related support parameters for inclusion in the CDD been identified, and has their basis as design requirements to affect availability, reliability, maintainability, interoperability, manpower, and logistics footprint, and the overall capability of the system to perform and endure in the required mission operational environment for subsequent phases been considered? | [5 empty] | 7.a(2)(a)
| HSI, T&E, logistics, risk, programmatic | (b) Has support related risk and risk mitigation planning for design and technology been identified? | [5 empty] | 7.a(2)(b)
| HSI, T&E, logistics, risk, programmatic | (c) Has support related risk and risk mitigation planning for future projections of domestic and foreign facilitation and logistics infrastructure been identified? | [5 empty] | 7.a(2)(c)
| T&E, HSI, logistics, risk, programmatic | (d) Has support related risk and risk mitigation planning for cost drivers been identified? | [5 empty] | 7.a(2)(d)
| HSI, PQM, T&E, software, training, logistics, EVM, technology, risk, programmatic, interoperability | (e) Have requirements for providing sustainment during Advanced Technology Demonstrations (ATDs), Advanced Concept Technology Demonstrations (ACTDs), and other technology oriented demonstrations been identified? | [5 empty] | 7.a(2)(e)
| T&E, HSI, logistics, programmatic | (3) Product Support Requirements | [5 empty] | 7.a(3)
| logistics, HSI, programmatic | (a) Has sustainment planning been prepared and assessed? | [5 empty] | 7.a(3)(a)
| logistics, HSI, programmatic | (b) Have sustainment planning parameters been recorded in the CDD? | [5 empty] | 7.a(3)(b)
| HSI, logistics, programmatic | (c) What is the product support acquisition strategy? | [5 empty] | 7.a(3)(c)
| HSI, logistics, programmatic | (d) What are the logistics, metrics, criteria, and funding requirements described in the Acquisition Program Baseline (APB)? | [5 empty] | 7.a(3)(d)
| T&E, HSI, logistics, programmatic | (e) What are the logistics considerations and test points described in the TEMP? | [5 empty] | 7.a(3)(e)
| HSI, risk, EVM, training, software, logistics, PQM, technology, T&E, programmatic, interoperability | b. Product Support Management | 0 | 0 | 0 | 0 | 0 | 7.b
| HSI, risk, EVM, training, software, logistics, PQM, technology, T&E, programmatic, interoperability | (1) Have deficiencies identified during previous assessments, program reviews, or testing been corrected? | [5 empty] | 7.b(1)
| HSI, logistics, programmatic | (2) Has an acquisition logistics support manager been assigned to the program office? | [5 empty] | 7.b(2)
| T&E, risk, logistics, HSI, programmatic | (3) Does supportability IPT have all applicable user representation? | [5 empty] | 7.b(3)
| HSI, logistics, programmatic | (4) Is a comprehensive logistics plan developed, documented, and implemented? | [5 empty] | 7.b(4)
| HSI, risk, EVM, training, software, logistics, PQM, technology, T&E, programmatic, interoperability | (5) Does material readiness planning and implementation include Lean Six Sigma (L6S) / theory of constraints concepts, Condition Based Maintenance Plus (CBM+) principles, and other systems engineering practices and methodologies throughout the acquisition and sustainment phases? | [5 empty] | 7.b(5)
| HSI, risk, EVM, training, software, logistics, PQM, technology, T&E, programmatic, interoperability | (6) Are metrics collected and processes selected for Continuous Process Improvement that demonstrate execution and the effectiveness of the effort? | [5 empty] | 7.b(6)
| HSI, logistics, programmatic | (7) Has the Product Support Plan (PSP) been updated to reflect the support concepts developed during the concept refinement phase? | [5 empty] | 7.b(7)
| HSI, risk, logistics, programmatic | (8) Does the PSP reflect and document evaluation of alternative logistics concepts and support system trade off results? | [5 empty] | 7.b(8)
| HSI, risk, logistics, programmatic, interoperability | (9) Does the PSP identify the impact of interoperability requirements? | [5 empty] | 7.b(9)
| T&E, risk, logistics, HSI, programmatic | (10) Have the comments of applicable commands been reviewed? | [5 empty] | 7.b(10)
| HSI, logistics, programmatic | (11) Are logistics metrics identified in the Acquisition Program Baseline (APB), and reflected in implementing logistics documentation? | [5 empty] | 7.b(11)
| logistics, T&E, training, programmatic | (12) Are Initial Operational Capability (IOC) / Full Operational Capability (FOC) dates established and defined? | [5 empty] | 7.b(12)
| risk, HSI, logistics, programmatic | (13) Are trade studies conducted on a continuous basis to ensure that performance and supportability goals are met? | [5 empty] | 7.b(13)
| risk, HSI, logistics, programmatic, interoperability | (14) Is logistic support included as a part of the life cycle SE approach to supportability, including information interoperability requirements? | [5 empty] | 7.b(14)
| risk, programmatic | (15) Has a risk management program been established that includes both Government and contractor participation? | [5 empty] | 7.b(15)
| risk, HSI, logistics, programmatic | (16) Have logistics support program risks and mitigation plans been identified and assessed? | [5 empty] | 7.b(16)
| HSI, risk, logistics, programmatic | (17) Are logistics support and overall sustainment performance requirements stated in the CDD? | [5 empty] | 7.b(17)
| T&E, HSI, logistics, programmatic | (18) Has the program office implemented a quality program to monitor contractor and vendor performance? | [5 empty] | 7.b(18)
| T&E, risk, logistics, programmatic | (19) Are there plans to ensure the quality program is properly staffed and assigned personnel will be accountable for product quality? | [5 empty] | 7.b(19)
| T&E, HSI, logistics, programmatic | (20) Are there plans to ensure the supply chain value stream will be mapped to the support process? | [5 empty] | 7.b(20)
| T&E, HSI, logistics, programmatic | (21) Are there plans to ensure the supply chain value stream process capabilities will be determined? | [5 empty] | 7.b(21)
| T&E, HSI, logistics, programmatic | (22) Are there plans to ensure the supply chain value stream process improvement initiatives will be implemented based on process capabilities? | [5 empty] | 7.b(22)
| T&E, HSI, logistics, programmatic | (23) Will the end-to-end logistics chain sustainment solutions have the flexibility to meet the full spectrum of contingencies with no loss of operational capability or tempo? | [5 empty] | 7.b(23)
| T&E, HSI, logistics, programmatic | (24) Will enterprise integration be enabled in a single view of the supply chain of both organic and commercial provider asset inventories and asset tracking (i.e., total asset visibility)? | [5 empty] | 7.b(24)
| logistics, T&E, risk, training, software, HSI, programmatic | c. PBL | 0 | 0 | 0 | 0 | 0 | 7.c
| T&E, HSI, logistics, programmatic | (1) Has Performance Based Logistics (PBL) been considered with support strategies consistent with the end-to-end material flow process, from factory to the ultimate customer? | [5 empty] | 7.c(1)
| T&E, HSI, logistics, risk, programmatic | (2) Have system level performance metrics been established for the Performance Based Acquisition (PBA) between the warfighter and the program manager? | [5 empty] | 7.c(2)
| T&E, logistics, HSI, training, software, programmatic | (3) Have PBL strategies been considered for all support areas (including technical assistance, support equipment, distance support, training, etc.) that incentivize performance, are metrics based, and consider legacy systems and Foreign Military Sales (FMS) participation? | [5 empty] | 7.c(3)
| HSI, risk, logistics, programmatic | d. Product Support Budgeting and Funding | 0 | 0 | 0 | 0 | 0 | 7.d
| HSI, logistics, programmatic | (1) Are logistics funding requirements developed using accepted cost estimating methodologies? | [5 empty] | 7.d(1)
| HSI, risk, logistics, programmatic | (2) Has the Logistics Requirements and Funding Summary (LRFS) or similar type document that identifies all appropriations including operations and maintenance funding been established and kept updated? | [5 empty] | 7.d(2)
| HSI, logistics, programmatic | (3) Does the LRFS support the budgetary requirements of the logistics support plan and requirements documentation? | [5 empty] | 7.d(3)
| HSI, logistics, programmatic | (4) Is the LRFS appropriately phased? | [5 empty] | 7.d(4)
| HSI, logistics, programmatic | (5) Are rationales to support the funding amounts in the LRFS documented? | [5 empty] | 7.d(5)
| HSI, logistics, programmatic | (6) Are the correct appropriations identified for each logistics requirement for each fiscal year? | [5 empty] | 7.d(6)
| HSI, risk, logistics, programmatic | (7) Are funding shortfalls and impacts identified, prioritized, fully documented and addressed to the program manager and resource sponsor? | [5 empty] | 7.d(7)
| HSI, logistics, programmatic | (8) Are the impacts of funding shortfalls understood? | [5 empty] | 7.d(8)
| HSI, risk, logistics, programmatic | (9) Are plans in place to mitigate risk? | [5 empty] | 7.d(9)
| HSI, logistics, programmatic | (10) Are LRFS numbers and dollars traceable to appropriate budget exhibits? | [5 empty] | 7.d(10)
| HSI, logistics, programmatic | (11) Have life cycle cost estimates, including cost reduction efforts, been developed and validated optimizing Total Ownership Costs (TOCs)? | [5 empty] | 7.d(11)
| HSI, logistics, programmatic | (12) Has the LRFS been staffed and approved? | [5 empty] | 7.d(12)
| HSI, logistics, programmatic | (13) Are funding requirements appropriately time phased? | [5 empty] | 7.d(13)
| T&E, PQM, logistics, risk, software, HSI, technology, programmatic | e. Design Interface (Reliability, Maintainability, and Availability (RMA)) | 0 | 0 | 0 | 0 | 0 | 7.e
| T&E, HSI, logistics | (1) Have all logistics requirements been considered in system requirements? | [5 empty] | 7.e(1)
| T&E, HSI, logistics, programmatic | (2) Have logistics support planning documents been updated to include Ao related information appropriate for this phase? | [5 empty] | 7.e(2)
| HSI, logistics, programmatic | (3) Have the support cost drivers been identified? | [5 empty] | 7.e(3)
| HSI, logistic | (4) Has supportability been considered in system requirements? | [5 empty] | 7.e(4)
| T&E, risk, logistics, HSI, programmatic | (5) Have Supportability Analysis (SA) planning documents been updated to include Ao related information appropriate for this phase? | [5 empty] | 7.e(5)
| T&E, HSI, logistics | (6) Have diagnostics requirements been addressed in system requirements? | [5 empty] | 7.e(6)
| T&E, HSI, software, logistics | (7) Are logistics elements are traceable to the Design Reference Mission Profile (DRMP)? | [5 empty] | 7.e(7)
| T&E, HSI, software, logistics | (a) Do the environmental profiles for the operating and non-operating requirements which consists of temperature, vibration, electromagnetic interference, electrostatic discharge, humidity, altitude, salt spray, fog, nuclear, chemical and biological, sand/dust, foreign object damage, production contaminants, etc., include system's production, operation and support environments with their associated timelines? | [5 empty] | 7.e(7)(a)
| T&E, HSI, logistics, risk, programmatic | (8) Are RMA / testability measures (e.g., Ao, Mean Time Between Failure (MTBF), Mean Time To Repair (MTTR) and Mean Logistics Delay Time (MLDT), Fault Detection, Fault Isolation and False Alarm) defined in quantifiable and measurable terms in the CDD? | [5 empty] | 7.e(8)
| T&E, risk, logistics, HSI | (9) Are RMA performance capability parameters defined consistent with the ICD / CDD and flowed down to the TEMP, Request for Proposal (RFP), contract and other programmatic documents? | [5 empty] | 7.e(9)
| T&E, HSI, logistics, programmatic | (10) Are appropriate RMA testability and PSP design analysis tests properly phased into the program? | [5 empty] | 7.e(10)
| T&E, HSI, logistics | (11) Are reliability and maintainability requirements adequately specified in the system specification and the TEMP? | [5 empty] | 7.e(11)
| T&E, HSI, logistics, programmatic | (12) Do DT and OT agree on test methodology for reliability and maintainability requirements? | [5 empty] | 7.e(12)
| T&E, HSI, logistics | (13) Have RMA supportability design guidelines been established? | [5 empty] | 7.e(13)
| T&E, HSI, logistics, programmatic | (14) Does the PSP identify when the Failure Modes, Effects and Criticality Analysis (FMECA) will be conducted and integrated with the SA program? | [5 empty] | 7.e(14)
| T&E, HSI, logistics | (15) Will service readiness improvement program and FMECA analyses be used to identify failure modes, their frequency, their effects on performance and their criticality, and be further used to develop condition based and schedule based maintenance tasks? | [5 empty] | 7.e(15)
| T&E, HSI, logistics | (16) Have actions been taken to ensure predictions, analyses and test results support RMA requirements? | [5 empty] | 7.e(16)
| T&E, software, HSI, logistics | (17) Will a readiness model be used to assess the effects of various levels of redundancies, spares, downtimes, and maintenance concepts on operational availability? | [5 empty] | 7.e(17)
| T&E, HSI, logistics | (18) Will contingencies for system selection or RMA supportability design changes be considered when preliminary RMA thresholds are deemed unachievable? | [5 empty] | 7.e(18)
| T&E, HSI, logistics, programmatic | (19) Is reliability development testing (test, analyze and fix) planned for Engineering and Manufacturing Development (EMD) phase? | [5 empty] | 7.e(19)
| T&E, HSI, logistics, programmatic | (20) Are Built In Test (BIT) and onboard diagnostics requirements adequately specified in the system specification and TEMP? | [5 empty] | 7.e(20)
| T&E, HSI, logistics, programmatic | (21) Is there a mechanism established for logisticians, engineers, and cost analysts to exchange data pertaining to the elements of system design and formal methods in place to review and document system design changes for impact on logistics support and program life cycle cost? | [5 empty] | 7.e(21)
| HSI, software, risk, logistics, technology, T&E, programmatic, interoperability | (22) Parts and Materials Selection | [5 empty] | 7.e(22)
| HSI, T&E, logistics, risk, programmatic | (a) Will guidance and / or requirements be documented in the parts and materials design guide before the start of design, addressing parts selection, de-rating, and testability factors, and will the adherence to the guidelines be verified at design reviews? | [5 empty] | 7.e(22)(a)
| HSI, T&E, software, logistics, risk, programmatic | (b) Is the reliability of identification of COTS / NDI required? | [5 empty] | 7.e(22)(b)
| HSI, T&E, logistics, risk, programmatic | (c) Is parts de-rating required for all electronic and electrical components, and are electrical parameters of parts characterized to requirements derived from the DRMP to ensure that all selected parts are reliable for the proposed application? | [5 empty] | 7.e(22)(c)
| HSI, risk, logistics, programmatic | (d) Are highly integrated parts used to reduce the number of individual discrete parts and chips? | [5 empty] | 7.e(22)(d)
| HSI, risk, logistics, programmatic | (e) Are highly integrated parts used to reduce the number of interconnections? | [5 empty] | 7.e(22)(e)
| HSI, risk, logistics, programmatic | (f) Are highly integrated parts used to reduce the size, power consumption, and cooling requirements? | [5 empty] | 7.e(22)(f)
| HSI, risk, logistics, programmatic | (g) Are highly integrated parts used to reduce the failure rates? | [5 empty] | 7.e(22)(g)
| PQM, logistics, technology, risk, programmatic, interoperability | (h) Does the design approach address the use of qualified manufacturers lists parts, particularly for applications requiring extended temperature ranges? | [5 empty] | 7.e(22)(h)
| PQM, logistics, technology, risk, programmatic, interoperability | (i) Is there a requirement for a preferred parts list and parts control prior to detailed design? | [5 empty] | 7.e(22)(i)
| HSI, T&E, logistics, programmatic | (23) Are design review requirements including supportability, flowed to design engineering from in-service data? | [5 empty] | 7.e(23)
| HSI, T&E, logistics, programmatic | (24) Are readiness reviews performed periodically throughout the life cycle and include supportability factors? | [5 empty] | 7.e(24)
| HSI, T&E, logistics, programmatic | (25) Has the program addressed standardization within the Acquisition Strategy (AS)? | [5 empty] | 7.e(25)
| HSI, T&E, logistics, programmatic | (26) Has the program established a process to reduce the proliferation of non-standard parts and equipment within and across system designs? | [5 empty] | 7.e(26)
| HSI, T&E, logistics, programmatic | (27) Do design and technical reviews include an assessment of system supportability requirements? | [5 empty] | 7.e(27)
| HSI, T&E, logistics, programmatic | (28) Is the testability BIT concept defined with the operational concept and the maintenance concept for all levels of maintenance? | [5 empty] | 7.e(28)
| HSI, logistics, software, T&E, programmatic, interoperability | f. Maintenance Planning | 0 | 0 | 0 | 0 | 0 | 7.f
| HSI, logistics, programmatic | (1) Has the initial maintenance concept been substantiated by non-economic Level of Repair Analysis (LORA) and documented in the PSP? | [5 empty] | 7.f(1)
| logistics, HSI | (2) Has the optimum maintenance concept been identified for the service readiness improvement plan, Condition Based Maintenance (CBM), CBM(+), and time base maintenance? | [5 empty] | 7.f(2)
| HSI, logistics, programmatic | (3) Have maintenance trade cost studies been conducted that support the prescribed maintenance concept? | [5 empty] | 7.f(3)
| logistics, HSI | (4) Are accessibility, diagnostics, repair and sparing concepts for all maintenance levels established? | [5 empty] | 7.f(4)
| HSI, logistics, programmatic | (5) Are requirements for manpower factors that impact system design utilization rates identified? | [5 empty] | 7.f(5)
| logistics, HSI | (6) Are life cycle supportability design, installation, maintenance and operating constraints and guidelines identified? | [5 empty] | 7.f(6)
| logistics, HSI, programmatic, interoperability | (7) Are maintenance planning and analyses consistent with requirements for USC Title 10 Core Government logistics maintenance capability and public / private partnering? | [5 empty] | 7.f(7)
| HSI, logistics, programmatic | (8) Is economic LORA planned and non-economic LORA performed? | [5 empty] | 7.f(8)
| HSI, logistics, programmatic | (9) Are serviced readiness improvement program analyses planned? | [5 empty] | 7.f(9)
| T&E, HSI, logistics, programmatic | (10) Has the maintenance concept been updated to include Ao related information appropriate for this phase? | [5 empty] | 7.f(10)
| logistics, HSI | (11) Have requirements been identified for special skills, maintenance and operator labor hours by rate by year, and number of personnel by rate, by maintenance level, and by year? | [5 empty] | 7.f(11)
| HSI, logistics, programmatic | (12) Will an on-condition status information system be defined, integrated and implemented for service readiness improvement programs? | [5 empty] | 7.f(12)
| T&E, risk, logistics, HSI, programmatic | (13) Will the maintenance plan define specific criteria for repair and maintenance for all applicable maintenance levels in terms of time, accuracy, repair levels, BIT, testability, reliability, maintainability, nuclear hardening, support equipment requirements (including automatic test equipment), manpower skills, knowledge and abilities and facility requirements for peacetime and wartime environments? | [5 empty] | 7.f(13)
| HSI, logistics, programmatic | (14) Have initial estimates of depot capability / capacity and resource requirements been made and documented? | [5 empty] | 7.f(14)
| logistics, HSI, software, programmatic | (15) Have funding requirements for interim support, transition planning, and establishment of organic capability been identified and documented in the LRFS? | [5 empty] | 7.f(15)
| HSI, T&E, logistics, programmatic, interoperability | g. Support Equipment | 0 | 0 | 0 | 0 | 0 | 7.g
| HSI, T&E, logistics, programmatic, interoperability | (1) Have the environmental and physical constraints, such as size, weight, power, temperatures and interfaces been factored into support equipment design? | [5 empty] | 7.g(1)
| HSI, T&E, logistics, programmatic, interoperability | (2) Will an analyses of automatic and manual fault detection and isolation equipment at each applicable maintenance level be conducted to identify the optimum mix? | [5 empty] | 7.g(2)
| logistics, HSI, programmatic | h. Supply Support Sparing Analysis | 0 | 0 | 0 | 0 | 0 | 7.h
| logistics, HSI, programmatic | (1) Has the maintenance philosophy been established? | [5 empty] | 7.h(1)
| logistics, HSI, programmatic | (2) Are initial sparing and modeling assumptions consistent with the prescribed maintenance concept? | [5 empty] | 7.h(2)
| risk, HSI, training, T&E, logistics, programmatic, interoperability | i. Manpower, Personnel and Training (MP&T) | 0 | 0 | 0 | 0 | 0 | 7.i
| training, HSI, logistics, programmatic, interoperability | (1) Have preliminary manpower estimates been identified? | [5 empty] | 7.i(1)
| training, HSI, logistics, programmatic, interoperability | (2) Have manpower and personnel requirements been identified for both organic and contractor support including knowledge, skills, and abilities? | [5 empty] | 7.i(2)
| training, HSI, logistics, programmatic | (3) Have manpower and personnel requirements been identified for both organic and contractor support including maintenance, operator and support provider labor hours by rate or skill area / level by year? | [5 empty] | 7.i(3)
| training, HSI, logistics, programmatic | (4) Have manpower and personnel requirements been identified for both organic and contractor support including the number of personnel by rate, maintenance level and year? | [5 empty] | 7.i(4)
| training, HSI, logistics, programmatic | (5) Have manpower and personnel requirements been identified for both organic and contractor support including the operator, maintainer and support provider organizational level assignments? | [5 empty] | 7.i(5)
| HSI, logistics | (6) Have maintenance task times, maintenance skill levels, and number of maintenance and support provider personnel required been derived from reliability? | [5 empty] | 7.i(6)
| HSI, logistics | (7) Have maintenance task times, maintenance skill levels, and number of maintenance and support provider personnel required been derived from maintainability? | [5 empty] | 7.i(7)
| HSI, logistics | (8) Have maintenance task times, maintenance skill levels, and number of maintenance and support provider personnel required been derived from availability? | [5 empty] | 7.i(8)
| HSI, training, logistics, programmatic, interoperability | (9) Does planning integrate manpower, personnel, and training, and does it considers the objectives identified in Sea Warrior, Total Force Strategy, and Integrated Logistics Environment (ILE) (or other ongoing initiatives)? | [5 empty] | 7.i(9)
| HSI, training, logistics, programmatic, interoperability | (10) Should planning include development of Joint Mission Essential Tasks Lists (JMETLs) to set priorities for joint exercises? | [5 empty] | 7.i(10)
| training, HSI, logistics, programmatic | (11) Has compatibility with military user career progression been evaluated? | [5 empty] | 7.i(11)
| training, HSI, logistics, programmatic | (12) Have peacetime and wartime manpower and personnel requirements been identified? | [5 empty] | 7.i(12)
| training, HSI, logistics, programmatic | (13) Have changes (increases and / or decreases) in manpower and personnel requirements been identified for any transition period between systems? | [5 empty] | 7.i(13)
| training, HSI, logistics, programmatic | (14) Have manpower and personnel requirements been affected by duties beyond operation, maintenance and support (e.g., watch standing, collateral duties)? | [5 empty] | 7.i(14)
| training, HSI, logistics, programmatic | (15) Has a Training Planning Process Methodology (TRPPM) been conducted? | [5 empty] | 7.i(15)
| training, HSI, logistics, programmatic | (16) Does the PSP reflect the results of the TRPPM analysis? | [5 empty] | 7.i(16)
| training, HSI, logistics, programmatic | (17) Has a applicable service training plan been developed and validated? | [5 empty] | 7.i(17)
| risk, training, logistics, HSI, programmatic | (18) Were the threshold requirements from the CDD used in the development of the MP&T requirements? | [5 empty] | 7.i(18)
| HSI, training, logistics, programmatic | (19) Does the explanation of manpower requirements clearly articulate qualifications and skills required? | [5 empty] | 7.i(19)
| risk, training, logistics, HSI, programmatic | (20) Is there a required operational capability / projected operational environment (or equivalent planning parameters) that addresses this system, and do the manpower requirements support these documents? | [5 empty] | 7.i(20)
| HSI, training, logistics, programmatic | (21) Does the applicable training plan reflect the most current manpower requirements data available, and are all billet requirements, specialty codes, rates and ratings identified? | [5 empty] | 7.i(21)
| training, T&E, logistics, HSI, programmatic | (22) Are training course requirements documented for Developmental Test and Evaluation (DT&E) and Operational Test and Evaluation (OT&E)? | [5 empty] | 7.i(22)
| training, HSI, logistics, programmatic, interoperability | (23) Is the acquisition strategy for Training Equipment and Devices (TE&D) documented? | [5 empty] | 7.i(23)
| logistics, HSI, training, programmatic | (24) Does the LRFS reflect funding for course and materials development factory training and TE&D? | [5 empty] | 7.i(24)
| training, HSI, logistics, programmatic | (25) Has the preliminary training system plan been prepared? | [5 empty] | 7.i(25)
| training, HSI, logistics, programmatic | (26) Will instructor guides, course curriculum, and student guides, as well as audio-visual training aids, be developed for classroom training? | [5 empty] | 7.i(26)
| training, HSI, logistics, programmatic | (27) Will training courses be conducted in a sufficient timeframe to support IOC / fielding? | [5 empty] | 7.(27)
| training, HSI, logistics, risk, programmatic | (28) Will contractor / Government T&E activities be used to validate training requirements? | [5 empty] | 7.i(28)
| risk, HSI, logistics, programmatic | j. Packaging, Handling, Storage and Transportation (PHS&T) | 0 | 0 | 0 | 0 | 0 | 7.j
| risk, HSI, logistics, programmatic | (1) Has a PHS&T plan been developed that identifies the program strategy for safely packaging, handling, storing, and transporting the system as well as any special requirements and interfaces with agencies or DoD components responsible for transporting the system? | [5 empty] | 7.j(1)
| risk, HSI, logistics, programmatic | (2) Have potential PHS&T related problems been identified, and are risk mitigation plans in place? | [5 empty] | 7.j(2)
| risk, HSI, logistics, programmatic | (3) Are PHS&T plans adequate to meet statutory and regulatory requirements, if new hazardous materials are being introduced? | [5 empty] | 7.j(3)
| risk, HSI, logistics, programmatic | (4) Does the LRFS identify PHS&T funding requirements? | [5 empty] | 7.j(4)
| HSI, risk, EVM, training, software, logistics, PQM, technology, T&E, programmatic, interoperability | k. Configuration Management (CM) | 0 | 0 | 0 | 0 | 0 | 7.k
| software, logistics, programmatic | (1) Is the CM plan in place and up to date? | [5 empty] | 7.k(1)
| software, risk, logistics, programmatic | (2) Does the CM plan address the methodology to manage system configuration throughout the program life cycle? | [5 empty] | 7.k(2)
| software, risk, logistics, programmatic | (3) Is the system requirement documented and being managed in accordance with the CM Plan? | [5 empty] | 7.k(3)
| software, logistics, programmatic | (4) Are changes to the managed Configuration Items (CI) controlled and tracked to higher level (system specification and CDD), and lower level (system requirements) documents? | [5 empty] | 7.k(4)
| HSI, risk, EVM, training, software, logistics, PQM, technology, T&E, programmatic, interoperability | (5) Does the CM plan define or link to the process for management of externally controlled requirements and SoS / FoS configurations? | [5 empty] | 7.k(5)
| HSI, risk, EVM, training, software, logistics, PQM, technology, T&E, programmatic, interoperability | l. Product and Technical Data | 0 | 0 | 0 | 0 | 0 | 7.l
| software, logistics, technology, programmatic | (1) Is technical data being acquired in digital electronic form enabling life cycle support using digital operations? | [5 empty] | 7.l(1)
| software, logistics, technology, programmatic | (2) Has a product technical data Concept of Operations (CONOPS) for acquiring and using digital product and technical data been developed and maintained throughout the system life cycle? | [5 empty] | 7.l(2)
| software, risk, technology, logistics, programmatic | (3) Does the product technical data CONOPS ensure that digital product and technical data is accessible and is interoperable with other programs and their interfacing logistics systems? | [5 empty] | 7.l(3)
| software, HSI, logistics, technology, programmatic | (4) Does the CONOPS ensure that product and technical data and data systems are reviewed and approved by the logistics Functional Area Manager (FAM)? | [5 empty] | 7.l(4)
| software, HSI, logistics, technology, programmatic | (5) Is logistics product technical data for new systems received, managed, and stored in FAM approved applications and or systems? | [5 empty] | 7.l(5)
| software, logistics, technology, programmatic | (6) Is the product and life cycle support operations automated and facilitated by using digital product and technical data? | [5 empty] | 7.l(6)
| HSI, risk, EVM, training, software, logistics, PQM, technology, T&E, programmatic, interoperability | (7) Has the project set up an integrated digital data environment to allow every activity involved with the program to cost effectively create, store, access, manipulate and / or exchange Ao, SE and SA data? | [5 empty] | 7.l(7)
| software, logistics, technology, programmatic | (8) Are electronic data interchange, on-line access, and automation issues addressed starting with development of the information exchange requirements and continuing through the program life cycle? | [5 empty] | 7.l(8)
| software, risk, logistics, technology, programmatic | (9) Has a product technical data management plan, guided by the product technical data CONOPS, including change control processes and in-process reviews, been developed and validated? | [5 empty] | 7.l(9)
| software, HSI, logistics, technology, programmatic | (10) Have the Technical Data Package (TDP) requirements been identified and documented in the PSP? | [5 empty] | 7.l(10)
| software, logistics, technology, programmatic | (11) Are full data rights being procured? | [5 empty] | 7.l(11)
| software, risk, logistics, technology, programmatic | (12) Has the potential effect on technical manual and engineering drawing development been considered and mitigated if commercial items are being procured? | [5 empty] | 7.l(12)
| software, HSI, logistics, technology, programmatic | (13) Is the level of technical data being procured consistent with levels of repair prescribed in the maintenance concept? | [5 empty] | 7.l(13)
| T&E, software, logistics, HSI, technology, programmatic | (14) Is the EMD contractor required to deliver source data packages for technical manuals and weapons loading manuals in time to support T&E events? | [5 empty] | 7.l(14)
| HSI, risk, logistics, T&E, training, PQM, programmatic, interoperability | m. Environment, Safety and Occupational Health (ESOH) | 0 | 0 | 0 | 0 | 0 | 7.m
| logistics, risk, programmatic | (1) Has a program to eliminate ESOH hazards or manage the risk where the hazard cannot be avoided been established? | [5 empty] | 7.m(1)
| HSI, risk, logistics, programmatic, interoperability | (2) Program Environmental, Safety and Health Evaluation (PESHE) | [5 empty] | 7.m(2)
| HSI, logistics, programmatic | (a) Has a PESHE been developed that describes the strategy for integrating ESOH considerations into the systems engineering process using the methodologies in the Standard Practice for System Safety, MIL-STD 882D? | [5 empty] | 7.m(2)(a)
| HSI, logistics, programmatic | (b) Has a PESHE been developed that describes the identification of responsibilities for implementing the ESOH strategy? | [5 empty] | 7.m(2)(b)
| HSI, logistics, programmatic | (c) Has a PESHE been developed that describes an approach to identify then eliminate ESOH hazards? | [5 empty] | 7.m(2)(c)
| HSI, risk, logistics, programmatic | (d) Has a PESHE been developed that describes implementation control for managing and mitigating ESOH risks where they cannot be avoided? | [5 empty] | 7.m(2)(d)
| HSI, risk, logistics, programmatic | (e) Has a PESHE been developed that describes identification and status of ESOH risks including approval by proper authority for residual ESOH risks (based on DoD policy and MIL-STD 882D)? | [5 empty] | 7.m(2)(e)
| HSI, risk, logistics, programmatic | (f) Has a PESHE been developed that describes the method for tracking progress? | [5 empty] | 7.m(2)(f)
| logistics, HSI, programmatic, interoperability | (g) Has a PESHE been developed that describes a schedule for completing National Environmental Policy Act (NEPA) / Executive Order (E.O.) 12114 documentation including the approval authority of the documents as detailed in DoD policy? | [5 empty] | 7.m(2)(g)
| HSI, risk, logistics, programmatic | (h) Has a PESHE been developed that describes identification of all Hazardous Materials (HAZMAT) and hazardous waste associated with the system and the plan for their demilitarization and disposal? | [5 empty] | 7.m(2)(h)
| logistics, HSI, programmatic, interoperability | (3) Is a Plan of Action and Milestones (POA&M) developed to identify significant program events to ensure NEPA or E.O. 12114 compliance? | [5 empty] | 7.m(3)
| HSI, PQM, T&E, logistics, training, programmatic | (4) National Environmental Policy Act (NEPA) Compliance Schedule | [5 empty] | 7.m(4)
| T&E, HSI, logistics, programmatic | (a) Does the NEPA compliance schedule include conducting test and evaluation of the system and / or subsystem? | [5 empty] | 7.m(4)(a)
| HSI, PQM, logistics, programmatic | (b) Does the NEPA compliance schedule include contracting for production? | [5 empty] | 7.m(4)(b)
| logistics, HSI, training, programmatic | (c) Does the NEPA compliance schedule include planning basing, training, and home porting locations? | [5 empty] | 7.m(4)(c)
| HSI, logistics, programmatic | (d) Does the NEPA compliance schedule include planning new or major upgrades to facilities or supporting infrastructure to support the system? | [5 empty] | 7.m(4)(d)
| HSI, logistics, programmatic | (e) Does the NEPA compliance schedule include demilitarization and disposal of the system? | [5 empty] | 7.m(4)(e)
| HSI, logistics, programmatic | (5) Does planning for NEPA require decisions that result in categorical exclusion, finding of no significant impact based upon an environmental assessment, and / or record of decision based upon an environmental impact statement? | [5 empty] | 7.m(5)
| HSI, logistics, programmatic | (6) NEPA Impact Assessments | [5 empty] | 7.m(6)
| HSI, logistics, programmatic | (a) Do specific NEPA impact assessments include Clean Water Act and National Pollutant Discharge Elimination System Permits? | [5 empty] | 7.m(6)(a)
| HSI, logistics, programmatic | (b) Do specific NEPA impact assessments include National Pollutant Discharge Elimination System Permits and the Marine Mammal Protection Act? | [5 empty] | 7.m(6)(b)
| HSI, logistics, programmatic | (c) Do specific NEPA impact assessments include the Clean Air Act? | [5 empty] | 7.m(6)(c)
| HSI, logistics, programmatic | (d) Do specific NEPA impact assessments include air permits? | [5 empty] | 7.m(6)(d)
| HSI, logistics, programmatic | (e) Do specific NEPA impact assessments include National Emissions Standards for Hazardous Air Pollutants? | [5 empty] | 7.m(6)(e)
| HSI, logistics, programmatic | (f) Do specific NEPA impact assessments include National Ambient Air Quality Standards? | [5 empty] | 7.m(6)(f)
| HSI, logistics, programmatic | (g) Do specific NEPA impact assessments include the Resource Conservation and Recovery Act? | [5 empty] | 7.m(6)(g)
| HSI, logistics, programmatic | (h) Do specific NEPA impact assessments include the Endangered Species Act? | [5 empty] | 7.m(6)(h)
| HSI, logistics, programmatic | (i) Do specific NEPA impact assessments include the Marine Mammal Protection Act? | [5 empty] | 7.m(6)(i)
| HSI, logistics, programmatic | (7) Has a system safety program to include interaction with systems engineering in accordance with MIL-STD 882 been established? | [5 empty] | 7.m(7)
| HSI, logistics, programmatic | (8) Have system safety design requirements been specified and legacy systems, subsystems, and components been analyzed and incorporated into the design requirements? | [5 empty] | 7.m(8)
| HSI, logistics, programmatic | (9) Does the program have a plan to recycle or dispose of system replaceable and disposable components, such as metals, plastics, electronic components, oils, coolants and refrigerants during system life and end of service life? | [5 empty] | 7.m(9)
| training, T&E, software, HSI, logistics, programmatic, interoperability | n. Facilities and Infrastructure | 0 | 0 | 0 | 0 | 0 | 7.n
| T&E, training, logistics, HSI, programmatic | (1) Have the types of facilities and infrastructure required to support and sustain the new or modified system been identified? | [5 empty] | 7.n(1)
| HSI, logistics, programmatic | (a) Are berthing spaces for ships (including utilities, dredging, special deck structural requirements for crane loads, and fendering systems) identified? | [5 empty] | 7.n(1)(a)
| HSI, logistics, programmatic | (b) Are parking aprons and hangar space for aircraft identified? | [5 empty] | 7.n(1)(b)
| logistics, HSI, training, programmatic | (c) Are support facilities, supply warehouses, transit sheds, maintenance facilities, dry dock capability, and training facilities (for both classrooms and trainers for operational training and maintenance training, including required product / technical data to ensure efficient, effective support of facilities) identified? | [5 empty] | 7.n(1)(c)
| HSI, logistics, programmatic | (d) Are transient support requirements when the system requires some level of support for continental United States (US) and outside continental US activities that are not regular homeports or support sites identified? | [5 empty] | 7.n(1)(d)
| HSI, logistics, programmatic | (2) Have Military Construction (MILCON) requirements been identified in the LRFS? | [5 empty] | 7.n(2)
| HSI, logistics, programmatic | (3) Does the PSP include analyses conducted to determine facility requirements? | [5 empty] | 7.n(3)
| HSI, logistics, programmatic | (4) Are facilities and infrastructure support requirements documented in the Facilities Management Plan (FMP)? | [5 empty] | 7.n(4)
| HSI, logistics, programmatic | (5) Is there a facilities requirements document and a schedule to conduct site surveys? | [5 empty] | 7.n(5)
| HSI, logistics, programmatic | (6) Is the facilities requirement development process integrated with the supportability analysis process? | [5 empty] | 7.n(6)
| logistics, HSI, programmatic, interoperability | (7) Has the Basic Facilities Requirements (BFR) been developed in accordance with the applicable service documents using the systems logistics support requirements? | [5 empty] | 7.n(7)
| logistics, HSI, programmatic, interoperability | (8) Have existing assets at each impacted shore activity been evaluated (e.g. site survey) to determine if they can be used to satisfy the BFRs associated with the new or modified system? | [5 empty] | 7.n(8)
| logistics, HSI, programmatic, interoperability | (9) Are the reasons for non-suitability documented and has an analysis of viable support alternatives been made to develop adequate facilities for the system, if existing assets at each impacted shore activity are not suitable? | [5 empty] | 7.n(9)
| logistics, HSI, programmatic, interoperability | (a) Has outsourcing (contractor operates Government owned) been considered? | [5 empty] | 7.n(9)(a)
| logistics, HSI, programmatic, interoperability | (b) Has privatization (Government buys services and relinquishes all interest including real estate and personal property) been considered? | [5 empty] | 7.n(9)(b)
| logistics, HSI, programmatic, interoperability | (c) Has leasing been considered? | [5 empty] | 7.n(9)(c)
| logistics, HSI, programmatic, interoperability | (d) Has repair / renovation / conversion of existing assets to satisfy requirements been considered? | [5 empty] | 7.n(9)(d)
| logistics, HSI, programmatic, interoperability | (e) Has new construction to provide required capability been considered? | [5 empty] | 7.n(9)(e)
| logistics, HSI, programmatic | (10) Has a designated source of repair and / or support, or work around been identified and received Fleet concurrence, if repair and / or support facilities cannot be completed in time to meet mission requirements and satisfy the BFR? | [5 empty] | 7.n(10)
| HSI, logistics, programmatic | (11) Have the estimates of facility requirements and associated cost been refined, and has detailed project documentation and cost estimates been developed? | [5 empty] | 7.n(11)
| HSI, software, logistics, programmatic, interoperability | (12) How is documentation of design related trade studies maintained in contractor databases? | [5 empty] | 7.n(12)
| logistics, HSI, programmatic, interoperability | (13) Does the Government have documented plans to review this data? | [5 empty] | 7.n(13)
| HSI, logistics, programmatic | (14) Is environmental documentation planning and completion in accordance with NEPA / EO 12114 either complete or scheduled for completion to support the timelines for new construction or modification of existing facilities? | [5 empty] | 7.n(14)
| HSI, logistics, programmatic | (15) Has the program assessed (e.g., site surveys and trade studies) all means of satisfying a facility requirement prior to selecting the use of MILCON? | [5 empty] | 7.n(15)
| HSI, logistics, programmatic | (16) Is the program assessment of satisfying a facility requirement prior to selecting the use of MILCON documented in the program's FMP or its equivalent? | [5 empty] | 7.n(16)
| logistics, programmatic | (17) Has the program office identified funding to support construction or alterations not classified as MILCON? | [5 empty] | 7.n(17)
| logistics, programmatic | (18) Is the contract award progress in a manner supportive of the ultimate need date? | [5 empty] | 7.n(18)
| logistics, programmatic | (19) Have projects (in excess of $750,000) classified as MILCON, been included in the applicable service project list? | [5 empty] | 7.n(19)
| logistics, programmatic | (20) Are projects classified as MILCON on track for Congressional approval? | [5 empty] | 7.n(20)
| logistics, programmatic | (21) Have estimates of facility requirements and associated costs been refined and detailed in project documentation, and have cost estimates been developed? | [5 empty] | 7.n(21)
| T&E, software, risk, logistic, programmatic, interoperability | o. Computer Resources and Software Support | 0 | 0 | 0 | 0 | 0 | 7.o
| risk, software, logistics, programmatic | (1) Has a computer and software security plan, including safety, been developed? | [5 empty] | 7.o(1)
| software, logistics, programmatic | (2) Is the program following the Defense Information Technology Security Certification and Accreditation Process? | [5 empty] | 7.o(2)
| software, logistics, programmatic | (3) Has the program developed a System Security Authorization Agreement (SSAA)? | [5 empty] | 7.o(3)
| software, logistics, programmatic | (4) Has the Computer Resources Working Group (CRWG) been established? | [5 empty] | 7.o(4)
| risk, software, logistics, programmatic, interoperability | (5) Have software functional requirements and associated interfaces been defined? | [5 empty] | 7.o(5)
| software, risk, logistics, programmatic | (6) Is planning in place to obtain data rights and licenses to make software available for reuse or export to other Government programs? | [5 empty] | 7.o(6)
| software, logistics, programmatic | (7) Has a software development plan been developed, and does it reflect program milestones? | [5 empty] | 7.o(7)
| software, logistics, programmatic | (8) Has a software CM plan been developed and / or included in program documentation? | [5 empty] | 7.o(8)
| software, T&E, logistics, programmatic | (9) Have measures of effectiveness been established for software? | [5 empty] | 7.o(9)
| HSI, logistics, technology, programmatic, interoperability | p. Automated Information Technology (AIT) | 0 | 0 | 0 | 0 | 0 | 7.p
| logistics, HSI, technology, programmatic, interoperability | (1) Have the Radio Frequency Identification (RFID) program plan and strategy been developed consistent with DoD policy? | [5 empty] | 7.p(1)
| logistics, HSI, technology, programmatic, interoperability | (2) Have RFID Defense Federal Acquisition Regulation Supplement (DFARS) clauses been added to all solicitations and contracts including DFARS Claus 252.211-7006RFID, and DFARS; RFID Interim Addendum (DFARS Case 2006-D002)? | [5 empty] | 7.p(2)
| logistics, HSI, technology, programmatic, interoperability | (3) Are program unique RFID requirements addressed in the program's PSP, LRFS, FMP, User Logistics Support Summary (ULSS), PBL Strategy, PHS&T planning documents, and maintenance Concepts? | [5 empty] | 7.p(3)
| logistics, HSI, technology, programmatic, interoperability | (4) Have RFID implementation and compliance metrics been identified? | [5 empty] | 7.p(4)
| logistics, HSI, technology, programmatic, interoperability | (5) Have the Unique Identification (UID) program plan and strategy been developed consistent with DoD policy? | [5 empty] | 7.p(5)
| logistics, HSI, technology, programmatic, interoperability | (6) Have UID DFARS clauses been added to all solicitations and contracts to include DFARS Clause 252.211-7003 Item Identification Evaluation? | [5 empty] | 7.p(6)
| logistics, HSI, technology, programmatic, interoperability | (7) Have program unique UID requirements been adequately addressed in the program's PSP, LRFS, FMP, ULSS PBL Strategy, PHS&T planning documents, and maintenance Concepts? | [5 empty] | 7.p(7)
| logistics, HSI, technology, programmatic, interoperability | (8) Have UID implementation and compliance metrics been identified? | [5 empty] | 7.p(8)
| logistics, T&E, software, PQM, technology, risk, programmatic, interoperability | q. Diminishing Manufacturing Sources and Material Shortages (DMSMS) | 0 | 0 | 0 | 0 | 0 | 7.q
| logistics, T&E, software, PQM, technology, risk, programmatic, interoperability | (1) Has a formal DMSMS program been established and documented consistent with DoD 4140.1-R, DoD Supply Chain Material Management Regulation, 23 May 2003? | [5 empty] | 7.q(1)
| logistics, T&E, software, PQM, technology, risk, programmatic, interoperability | (2) Has a formal DMSMS program been established and documented consistent with ASN (RD&A) memorandum dated 27 January 2005, “DMSMS Management Guidance.”? | [5 empty] | 7.q(2)
| logistics, T&E, software, PQM, technology, risk, programmatic, interoperability | (3) Has a formal DMSMS program been established and documented consistent with DASN(L) memorandum dated 12 April 2005, “DMSMS Program Management Plans and Metrics” (and attached Management Plan Guidance)? | [5 empty] | 7.q(3)
| logistics, T&E, software, PQM, technology, risk, programmatic, interoperability | (4) Has a formal DMSMS program been established and documented consistent with ASN (RD&A) memo of 12 May 2006, "DMSMS Guidance for Developing Contractual Requirements (and attached Contractual Guidance)? | [5 empty] | 7.q(4)
| logistics, T&E, software, PQM, technology, risk, programmatic, interoperability | (5) Is the DMSMS strategy integrated with the program’s technology roadmap, as well as the industry technology roadmaps for embedded microelectronics? | [5 empty] | 7.q(5)
| logistics, T&E, software, PQM, technology, risk, programmatic, interoperability | (a) Does the road mapping process consider identification of critical items and technologies? | [5 empty] | 7.q(5)(a)
| logistics, T&E, software, PQM, technology, risk, programmatic, interoperability | (b) Does the road mapping process consider identification of emerging technologies? | [5 empty] | 7.q(5)(b)
| logistics, T&E, software, PQM, technology, risk, programmatic, interoperability | (6) Does the design approach minimize the impact of DMSMS by addressing open system architecture? | [5 empty] | 7.q(6)
| risk, PQM, logistics, technology, programmatic, interoperability | (a) Does the design approach minimize the impact of DMSMS by addressing the order of precedence for parts selection? | [5 empty] | 7.q(6)(a)
| logistics, T&E, software, PQM, technology, risk, programmatic, interoperability | (b) Does the design approach minimize the impact of DMSMS by addressing the application specific integrated circuits vs. field programmable gate arrays? | [5 empty] | 7.q(6)(b)
| logistics, PQM, technology, risk, programmatic, interoperability | (c) Does the design approach minimize the impact of DMSMS by addressing minimizing the use of custom parts? | [5 empty] | 7.q(6)(c)
| logistics, T&E, software, PQM, technology, risk, programmatic, interoperability | (7) Do design reviews address DMSMS management approaches and solutions? | [5 empty] | 7.q(7)
| logistics, T&E, software, PQM, technology, risk, programmatic, interoperability | (8) Has an exit strategy been developed and is it contained in contractual / PBL documentation that provides DMSMS configuration data access necessary to transition product support capability? | [5 empty] | 7.q(8)
| logistics, T&E, software, PQM, technology, risk, programmatic, interoperability | (9) Do contractual data requirements define requirements for the contractor to define and implement DMSMS management program? | [5 empty] | 7.q(9)
| Level 1, HSI, T&E, technology, risk, PQM, logistics, software, training, programmatic, interoperability | 8. System Requirements | 0 | 0 | 0 | 0 | 0 | 8
| software, T&E, technology, programmatic, interoperability | a. Are you aligned with Net-Centric Operations and Warfare functional concept? | [5 empty] | 8.a
| software, T&E, technology, programmatic, interoperability | b. Does the system conform with Net-Centric Operations and Warfare System / Technical Requirements? | 0 | 0 | 0 | 0 | 0 | 8.b
| software, T&E, technology, programmatic, interoperability | (1) Has the system been mapped to the common system function list? | [5 empty] | 8.b(1)
| software, T&E, technology, programmatic, interoperability | (2) Does the system intend to employ an Internet Protocol (IP) based network, will it be IPv6 compatible by 2008, or is there a reasonable transition plan? | [5 empty] | 8.b(2)
| software, T&E, technology, programmatic, interoperability | (3) Have data exchange requirements been identified that comply with DoD directed Architectures? | [5 empty] | 8.b(3)
| logistics, HSI, software, T&E, technology, programmatic, interoperability | c. Net-Centric Operations and Warfare Policy Requirements Conformance | 0 | 0 | 0 | 0 | 0 | 8.c
| logistics, HSI, software, T&E, technology, programmatic, interoperability | (1) Will the system be compliant with HSI Compliance Action List (CAL)? | [5 empty] | 8.c(1)
| logistics, HSI, software, T&E, technology, programmatic, interoperability | (2) Will the system be compliant with E3 / Spectrum Supportability CAL? | [5 empty] | 8.c(2)
| logistics, HSI, software, T&E, technology, programmatic, interoperability | (3) Will the system be compliant with Information Assurance (IA) CAL? | [5 empty] | 8.c(3)
| logistics, HSI, software, T&E, technology, programmatic, interoperability | (4) Will the system be compliant with the Geospatial / Time Standards (GTS) CAL? | [5 empty] | 8.c(4)
| software, HSI, logistics, PQM, T&E, technology, programmatic, interoperability | d. Requirements Management | 0 | 0 | 0 | 0 | 0 | 8.d
| software, T&E, logistics, programmatic | (1) Is there a process in place for requirements management, and is it being applied to properly address this stage of the program? | [5 empty] | 8.d(1)
| software, T&E, logistics, programmatic | (2) Are requirements being managed and traced from higher level (parent) requirements to lower level (offspring) requirements? | [5 empty] | 8.d(2)
| software, T&E, logistics, programmatic | (3) Are there any “orphan” or “childless” requirements? | [5 empty] | 8.d(3)
| logistics, T&E, software, PQM, programmatic | (4) Is adequate requirements traceability in place to ensure compliance with the CDD / Capability Production Document (CPD)? | [5 empty] | 8.d(4)
| logistics, HSI, software, T&E, technology, programmatic, interoperability | (5) Have all applicable requirements documents (i.e. Global Information Grid (GIG), Theater, Air, and Missile Defense (TAMD), etc.) been identified? | [5 empty] | 8.d(5)
| logistics, T&E, software, programmatic | (6) Are both effectiveness and suitability requirements being addressed in the systems requirements? | [5 empty] | 8.d(6)
| PQM, HSI, software, logistics, T&E, programmatic | (7) Does analyses of preliminary designs and processes indicate that identification and management of critical safety items are being considered at the air vehicle level, and are being flowed down to the subsystem and component levels? | [5 empty] | 8.d(7)
| logistics, software, T&E, programmatic | e. Are system requirements traced to the CDD? | [5 empty] | 8.e
| software, T&E, training, risk, logistics, PQM, technology, HSI, programmatic, interoperability | f. Overall System Requirements | 0 | 0 | 0 | 0 | 0 | 8.f
| T&E, software, logistics, risk, technology, programmatic, interoperability | (1) Have the KPPs and other performance requirements, both explicit and derived for the overall system been defined, quantified and documented? | [5 empty] | 8.f(1)
| logistics, software, T&E, programmatic | (2) Have all of the explicit and derived system requirements and system constraints for the overall system been documented in the system specification? | [5 empty] | 8.f(2)
| software, T&E, logistics, technology, programmatic | (3) Are derived requirements (Critical Technical Parameters (CTPs) / Critical Operational Issues (COIs)) for the overall system traceable to system requirements? | [5 empty] | 8.f(3)
| logistics, software, T&E, programmatic | (4) Have airworthiness requirements for the overall system been addressed and documented in the system specification? | [5 empty] | 8.f(4)
| HSI, T&E, logistics, programmatic | (5) Have Reliability, Maintainability and Built In Test (BIT) requirements for the overall system been addressed in the system requirements? | [5 empty] | 8.f(5)
| software, T&E, logistics, technology, programmatic, interoperability | (6) Have system architectural requirements (both explicit and implied) been addressed? | [5 empty] | 8.f(6)
| software, T&E, logistics, technology, programmatic, interoperability | (7) Can support for the partitioning rationale be found in the existing architecture documents, and does the architectural development process support early identification and resolution of top level design issues? | [5 empty] | 8.f(7)
| software, risk, logistics, T&E, technology, programmatic, interoperability | (8) Are unique system features, use of off-the-shelf software, application of industry standards, and the relationship of the system architecture to DOD standards documented, and have methods of risk management been identified? | [5 empty] | 8.f(8)
| HSI, software, T&E, logistics, programmatic, interoperability | (9) Electromagnetic Environmental Effects (E3) and Spectrum Supportability | [5 empty] | 8.f(9)
| HSI, T&E, logistics, programmatic | (a) Does the CDD address spectrum certification compliance, spectrum supportability, host nation approval, the control of E3, and safety issues regarding the Hazards of Electromagnetic Radiation to Ordnance (HERO)? | [5 empty] | 8.f(9)(a)
| HSI, T&E, logistics, programmatic | (b) Have DD1494 form(s) been completed and submitted for all Radio Frequency (RF) spectrum dependent equipment? | [5 empty] | 8.f(9)(b)
| HSI, T&E, logistics, programmatic | (c) Have the requirements for electromagnetic spectrum supportability assessment factors been completed and submitted for spectrum supportability approval to support a Milestone (MS) B decision? | [5 empty] | 8.f(9)(c)
| HSI, T&E, logistics, programmatic, interoperability | (d) Has the integrated topside design analysis / study been initiated for adding an antenna or aperture to the ship's topside environment? | [5 empty] | 8.f(9)(d)
| HSI, T&E, logistics, programmatic | (e) Has the intended Operational Electromagnetic Environment (EME), as represented in the MIL-STD-464A, been defined? | [5 empty] | 8.f(9)(e)
| HSI, software, T&E, logistics, programmatic | (f) Have all the box level requirements of MIL-STD-461E been addressed? | [5 empty] | 8.f(9)(f)
| HSI, T&E, logistics, programmatic | (g) Have all the aircraft system level requirements of MIL-STD-464A including electrical bonding, Precipitation Static (P-static), Electrostatic Discharge (ESD), subsystem Electromagnetic Interference (EMI) (including COTS and NDI), intra-system Electromagnetic Compatibility (EMC), inter-system EMC and High Intensity Radiated Fields (HIRF), lightening effects (direct and indirect), Hazards of Electromagnetic Radiation to Ordnance (HERO), Hazards of Electromagnetic Radiation to Personnel (HERP), Hazards of Electromagnetic Radiation to Fuel (HERF), TEMPEST, and Electromagnetic Pulse (EMP) effects, and life cycle E3 hardening been addressed? | [5 empty] | 8.f(9)(g)
| HSI, T&E, logistics, programmatic | (h) Does the program schedule allow adequate time between prototyping and first flight to conduct flight worthiness EMI testing? | [5 empty] | 8.f(9)(h)
| HSI, T&E, logistics, programmatic | (i) Does the program schedule allow adequate time to correct EMI deficiencies prior to production start? | [5 empty] | 8.f(9)(i)
| HSI, T&E, logistics, programmatic | (j) Has the requirement and funding for a facility to conduct EMI / EMC demonstration testing been established? | [5 empty] | 8.f(9)(j)
| HSI, T&E, logistics, programmatic | (k) Are E3 and spectrum management included in the SOW, CDRLs and CLINES? | [5 empty] | 8.f(9)(k)
| T&E, HSI, PQM, logistics, risk, programmatic | (10) Have quality and producibility requirements been considered throughout the supply chain? | [5 empty] | 8.f(10)
| HSI, PQM, logistics, programmatic | (a) Has a manufacturing plan been developed to include short term and long term Full Rate Production (FRP) requirements including the time phasing of all resource requirements (e.g., personnel, machines, tooling, measurement system, supply chain, etc.)? | [5 empty] | 8.f(10)(a)
| HSI, PQM, logistics, programmatic | (b) Has a manufacturing plan been developed to include a defect variation prevention program? | [5 empty] | 8.f(10)(b)
| HSI, PQM, logistics, programmatic | (c) Has a manufacturing plan been developed to include manufacturing processes that have defined yield levels and have been validated? | [5 empty] | 8.f(10)(c)
| HSI, T&E, logistics, PQM, programmatic | (d) Has a manufacturing plan been developed to include environmental stress screening to precipitate latent, intermittent or incipient defects, or flaws introduced during the manufacturing process? | [5 empty] | 8.f(10)(d)
| PQM, risk | (e) Have plans been made to address issues associated with an industrial base capability assessment? | [5 empty] | 8.f(10)(e)
| PQM, risk | (f) Does the program provide for the selection of suppliers on the basis of their ability to perform satisfactorily based on evidence of capability? | [5 empty] | 8.f(10)(f)
| PQM, risk | (g) Does the quality program assure that manufacturing will be accomplished under controlled conditions (work instructions, adequate production equipment, special environments)? | [5 empty] | 8.f(10)(g)
| T&E, HSI, logistics, risk, programmatic | (11) Does the design for human system safety (new, baseline, modification) require preliminary hazard analyses, operating and support hazard analyses, safety assessment report analyses, and hazard tracking and risk solution analyses? | [5 empty] | 8.f(11)
| T&E, HSI, logistics, risk, programmatic | (12) Have aeromechanics requirements been considered? | [5 empty] | 8.f(12)
| T&E, HSI, logistics, risk, programmatic | (13) Have structures requirements been considered? | [5 empty] | 8.f(13)
| T&E, HSI, logistics, risk, programmatic | (14) Does the design for materials (new, baseline, modification) require preliminary hazard analyses, operating and support hazard analyses, safety assessment report analyses, and hazard tracking and risk solution analyses? | [5 empty] | 8.f(14)
| software, T&E, logistics, HSI, training, PQM, technology, programmatic | (15) Have human interfaces, human performance and error avoidance been considered in the following human SE requirements for the system? | [5 empty] | 8.f(15)
| software, T&E, logistics, HSI, training, PQM, technology, programmatic | (a) Has the program developed training systems plans to maximize use of new learning techniques, modeling and simulation technology, embedded training, and instrumentation systems that provide anytime, anyplace training, while reducing the demand on the training establishment? | [5 empty] | 8.f(15)(a)
| training, HSI, logistics, programmatic | (I) Was a Training System Requirements Analysis (TSRA) conducted? | [5 empty] | 8.f(15)(a)(I)
| training, T&E, logistics, HSI, programmatic | (II) Were embedded training capabilities considered? | [5 empty] | 8.f(15)(a)(II)
| PQM, logistics | (b) Was the system design for usability? | [5 empty] | 8.f(15)(b)
| PQM, logistics | (c) Was the system design for maintainability? | [5 empty] | 8.f(15)(c)
| programmatic, logistics, HSI | (d) Was the system task and equipment standardized? | [5 empty] | 8.f(15)(d)
| programmatic, HSI | (e) Has the system considered aviation life support / aircrew escape and survival? | [5 empty] | 8.b(15)(e)
| HSI, logistics | (f) Does HSI analysis address accessibility? | [5 empty] | 8.f(15)(f)
| HSI, logistics | (g) Does HSI analysis address visibility? | [5 empty] | 8.f(15)(g)
| HSI, logistics | (h) Does HSI analysis address the human factors and ergonomics? | [5 empty] | 8.f(15)(h)
| HSI, logistics | (i) Does HSI analysis address the testability and BIT? | [5 empty] | 8.f(15)(i)
| HSI, logistics | (j) Does HSI analysis address the complexity? | [5 empty] | 8.f(15)(j)
| HSI, logistics | (k) Does HSI analysis address the standardization and interchangeability? | [5 empty] | 8.f(15)(k)
| HSI, logistics | (l) Does HSI analysis address the use of mockups, modeling, and simulation? | [5 empty] | 8.f(15)(l)
| HSI, logistics | (m) Does HSI analysis address the operational experience? | [5 empty] | 8.f(15)(m)
| HSI, logistics | (n) Does HSI analysis address the workspace environment (heating, cooling, ventilation, illumination, noise, and vibration)? | [5 empty] | 8.f(15)(n)
| HSI, logistics | (o) Does HSI analysis address the design for effective handling and carrying? | [5 empty] | 8.f(15)(o)
| HSI, logistics | (p) Does HSI analysis address the controls and displays? | [5 empty] | 8.f(15)(p)
| HSI, logistics | (q) Does HSI analysis address the user computer interface? | [5 empty] | 8.f(15)(q)
| HSI, logistics | (r) Does HSI analysis address the safety and survivability? | [5 empty] | 8.f(15)(r)
| logistics, HSI | (s) Have broad cognitive, physical and sensory requirements for the operators, maintainers and support personnel that contribute or constrain to total system performance been analyzed? | [5 empty] | 8.f(15)(s)
| HSI, T&E, logistics, programmatic | (t) Have contractual provisions been made to allow for adequate HSI simulations using mockups, models or computer simulations for engineering change proposals? | [5 empty] | 8.f(15)(t)
| HSI, T&E, logistics, programmatic | (u) Has an HSI plan been developed, resourced, executed and maintained, and been coordinated with subsystem HSI plans and the overall SEP? | [5 empty] | 8.f(15)(u)
| HSI, T&E, logistics, programmatic | (v) Has the SEP been updated to include Ao related information appropriate for this phase? | [5 empty] | 8.f(15)(v)
| HSI, logistics, programmatic | (16) Has the quality of life been considered in the system requirements? | [5 empty] | 8.f(16)
| HSI, software, risk, T&E, logistics, programmatic, interoperability | (17) Is there sufficient functional detail to enable detailed design (i.e. development of program performance specifications) for computer and software CIs to perform coding? | [5 empty] | 8.f(17)
| HSI, software, logistics | (a) Are the software safety, security, and privacy requirements fully defined to enable functional decomposition? | [5 empty] | 8.f(17)(a)
| logistics, HSI, programmatic, interoperability | (b) Are software interoperability requirements fully defined to enable functional decomposition? | [5 empty] | 8.f(17)(b)
| HSI, software, risk, T&E, logistics, programmatic, interoperability | (c) Are internal and external interfaces fully defined, documented, and accepted by all affected parties to enable functional decomposition? | [5 empty] | 8.f(17)(c)
| risk, T&E, logistics, software, HSI, programmatic | (18) Does the program provide adequate schedule and resources to conduct antenna performance, and corrective measures? | [5 empty] | 8.f(18)
| software, T&E, logistics, HSI, programmatic | g. Are the system requirements of each CI consistent with the subsystem test planning and approach? | [5 empty] | 8.g
| HSI, T&E, logistics, programmatic | h. Test Requirements | 0 | 0 | 0 | 0 | 0 | 8.h
| HSI, T&E, logistics, programmatic | (1) Are requirements testable and verifiable? | [5 empty] | 8.h(1)
| HSI, T&E, logistics, programmatic | (2) Has the Ao portion of test plans been defined or updated for this phase of the program? | [5 empty] | 8.h(2)
| HSI, T&E, logistics, programmatic | (3) Are HSI metrics incorporated into the program's T&E activities? | [5 empty] | 8.h(3)
| HSI, T&E, logistics, programmatic | (4) Is the interoperability KPP testing planned and resources identified? | [5 empty] | 8.h(4)
| Level 1, T&E, software, HSI, logistics, risk, programmatic, interoperability | 9. Technology Development | 0 | 0 | 0 | 0 | 0 | 9
| T&E, HSI, logistics, programmatic | a. Has the program identified and documented a standard methodology for conducting Ao analysis? | [5 empty] | 9.a
| T&E, HSI, logistics, programmatic, interoperability | b. Is the methodology consistent with DoD guidelines? | [5 empty] | 9.b
| T&E, HSI, logistics, programmatic | c. Is the methodology consistent with best commercial practices and within the budget and programmatic limitations? | [5 empty] | 9.c
| T&E, HSI, logistics, programmatic | d. What are the definitive references for the program methodology for Ao, and where is the method described? | [5 empty] | 9.d
| logistics, HSI, software, T&E, programmatic | e. System Modeling | 0 | 0 | 0 | 0 | 0 | 9.e
| logistics, HSI, software, T&E, programmatic | (1) Has the program team identified a single or a family of models for conducting Ao analysis? | [5 empty] | 9.e(1)
| logistics, HSI, software, T&E, programmatic | (2) What parametric (top down) model(s) have been selected? | [5 empty] | 9.e(2)
| logistics, HSI, software, T&E, programmatic | (3) What engineering estimate (bottoms up) model(s) have been selected? | [5 empty] | 9.e(3)
| logistics, HSI, software, T&E, programmatic | (4) Where are the parametric models and engineering estimate models documented? | [5 empty] | 9.e(4)
| T&E, HSI, logistics, software, risk, programmatic, interoperability | f. Are the same methods and models used by all (contractor and Government) agencies that perform and conduct decision support analysis for Ao for this program? | [5 empty] | 9.f
| HSI, logistics, software, risk, programmatic | g. Have cost and schedule impacts for supportability and logistics risk mitigation been documented and identified in the LRFS? | [5 empty] | 9.g
| T&E, HSI, logistics, software, risk, programmatic | h. Are T&E members utilizing the program risk management system? | [5 empty] | 9.h
| Level 1, software, T&E, logistics, EVM, training, risk, PQM, HSI, technology, programmatic, interoperability | 10. System Verification | 0 | 0 | 0 | 0 | 0 | 10
| T&E, logistics, training, software, HSI, EVM, PQM, technology, risk, programmatic, interoperability | a. Verification Programmatic | 0 | 0 | 0 | 0 | 0 | 10.a
| T&E, logistics, training, software, HSI, EVM, PQM, technology, risk, programmatic, interoperability | (1) Has the program identified standard ground rules and assumptions for use by all agencies supporting program analysis? | [5 empty] | 10.a(1)
| T&E, HSI, logistics, programmatic | (2) Are work hour rates for operators and maintainers defined? | [5 empty] | 10.a(2)
| T&E, HSI, logistics, programmatic | (3) Are operating hours per / system / per / year defined? | [5 empty] | 10.a(3)
| T&E, HSI, logistics, PQM, programmatic | (4) Are production, deployment schedules defined? | [5 empty] | 10.a(4)
| T&E, HSI, logistics, programmatic | (5) Are site "stand up" schedules defined? | [5 empty] | 10.a(5)
| T&E, HSI, logistics, programmatic | (6) Are the phase-in and phase-out for (new / old) systems defined? | [5 empty] | 10.a(6)
| HSI, logistics, technology, T&E, programmatic | (7) Are technology refreshment schedules defined? | [5 empty] | 10.a(7)
| T&E, HSI, logistics, programmatic | (8) Has the economic life (for analysis purposes) been defined? | [5 empty] | 10.a(8)
| T&E, HSI, logistics, programmatic | (9) Has the DRMP been defined? | [5 empty] | 10.a(9)
| T&E, logistics, training, software, HSI, EVM, PQM, technology, risk, programmatic, interoperability | (10) Where are the ground rules and assumptions documented, and how do all analysis agencies obtain this information? | [5 empty] | 10.a(10)
| HSI, PQM, logistics, programmatic, interoperability | b. Verification Costing | 0 | 0 | 0 | 0 | 0 | 10.b
| HSI, PQM, logistics, programmatic, interoperability | (1) Have all initial production and recurring support costs been included in the analysis capability? | [5 empty] | 10.b(1)
| HSI, PQM, logistics, programmatic, interoperability | (2) Are all future costs covered to include customer costs, contractor costs, supplier costs, third party provider costs, direct and indirect costs, variable and fixed costs, design and development costs, production and construction costs, operation and support costs, retirement costs, and material recycling / disposal costs? | [5 empty] | 10.b(2)
| HSI, logistics, programmatic | (3) Have any costs or logistics elements been identified for elimination from any specific analysis? | [5 empty] | 10.b(3)
| HSI, logistics, programmatic | (4) Has the rational to eliminate any costs or logistics elements been documented, and where? | [5 empty] | 10.b(4)
| HSI, logistics, programmatic | (5) Have all funding shortfalls been identified and prioritized? | [5 empty] | 10.b(5)
| T&E, HSI, logistics, risk, programmatic | c. System Support | 0 | 0 | 0 | 0 | 0 | 10.c
| T&E, HSI, logistics, risk, programmatic | (1) What rate of "cannibalization" will be allowed in analyzing Ao for this program? | [5 empty] | 10.c(1)
| T&E, HSI, logistics, programmatic | (2) Has the effect of cannibalization on equipment reliability (accelerated wear out), maintenance induced failures, and manpower turnover been included in the analysis? | [5 empty] | 10.c(2)
| HSI, logistics, programmatic | (3) Has the rate(s) of cannibalization versus spares costs been documented? | [5 empty] | 10.c(3)
| HSI, logistics, programmatic | (4) Has the user been briefed and accepted the systems support to this aspect of analysis? | [5 empty] | 10.c(4)
| HSI, logistics, programmatic | d. What planning factors been reviewed and approved by applicable agencies such as DoD, and service chiefs? | [5 empty] | 10.d
| T&E, HSI, logistics, programmatic | e. System Availability and Performance | 0 | 0 | 0 | 0 | 0 | 10.e
| T&E, HSI, logistics, programmatic | (1) Have the Ao related objectives and thresholds been defined? | [5 empty] | 10.e(1)
| T&E, HSI, logistics, programmatic | (2) Has the system analysis been updated for this phase of the program? | [5 empty] | 10.e(2)
| T&E, HSI, logistics, programmatic | (3) Has Ao tracking been analyzed appropriately for this phase? | [5 empty] | 10.e(3)
| T&E, HSI, logistics, programmatic | (4) Is there any need to re-baseline the program objectives and thresholds using Cost as an Independent Variable (CAIV) guidelines? | [5 empty] | 10.e(4)
| T&E, HSI, logistics, programmatic | f. Are detailed design related Ao drivers being identified at the appropriate WBS for this phase? | [5 empty] | 10.f
| Level 1, T&E, logistics, training, software, HSI, EVM, PQM, technology, risk, programmatic, interoperability | 11. Program Risk Assessment | 0 | 0 | 0 | 0 | 0 | 11
| risk, software, programmatic | a. Have risk items in the system requirements been defined and analyzed? | [5 empty] | 11.a
| risk, T&E, logistics, HSI, programmatic | b. How has risk analysis been incorporated in to Ao analysis? | [5 empty] | 11.b
| software, risk, technology, programmatic | c. Is the risk assessment process tightly coupled with the technical effort and reflective of the technical risks inherent in the system requirements? | [5 empty] | 11.c
| software, risk, programmatic | d. Has the risk assessment addressed future risks to development? | [5 empty] | 11.d
| T&E, logistics, training, software, HSI, EVM, PQM, technology, risk, programmatic, interoperability | e. Is there adequate agreement among the technical team concerning the risks? | [5 empty] | 11.e
| T&E, logistics, training, software, HSI, EVM, PQM, technology, risk, programmatic, interoperability | f. Have cost and schedule impacts been defined for mitigation options? | [5 empty] | 11.f
| T&E, logistics, training, software, HSI, EVM, PQM, technology, risk, programmatic, interoperability | g. Is the technical risk assessment being shared at all levels of the program team? | [5 empty] | 11.g
| HSI, risk, logistics, programmatic | h. Have supportability and logistics risk items been defined, analyzed, and included in the program risk assessment? | [5 empty] | 11.h
| HSI, risk, logistics, programmatic | i. Have cost and schedule impacts for supportability and logistics risk mitigation been documented and identified in the LRFS? | [5 empty] | 11.i
| risk, T&E, programmatic | j. Are T&E members utilizing the program risk management system? | [5 empty] | 11.j
| Level 1, T&E, logistics, training, software, HSI, EVM, PQM, technology, risk, programmatic, interoperability | 12. Completion / Exit Criteria | 0 | 0 | 0 | 0 | 0 | 12
| T&E, logistics, training, software, HSI, EVM, PQM, technology, risk, programmatic, interoperability | a. Were SRR issues captured in RFAs and properly adjudicated and assigned? | [5 empty] | 12.a
| T&E, logistics, training, software, HSI, EVM, PQM, technology, risk, programmatic, interoperability | b. Were all SRR RFAs properly completed (closed)? | [5 empty] | 12.b
| T&E, logistics, training, software, HSI, EVM, PQM, technology, risk, programmatic, interoperability | c. Were the proper technical disciplines represented at the review? | [5 empty] | 12.c
| T&E, software, logistics, programmatic | d. Can the system requirements, as disclosed, satisfy the CDD? | [5 empty] | 12.d
| T&E, software, logistics, programmatic | e. Are the system requirements sufficiently detailed and understood to enable system functional definition and functional decomposition? | [5 empty] | 12.e
| T&E, software, logistics, programmatic | f. Is there an approved system specification? | [5 empty] | 12.f
| T&E, software, logistics, programmatic | g. Are adequate processes and metrics in place for the program to succeed? | [5 empty] | 12.g
| software, T&E, logistics, HSI, programmatic | h. Are the risks known and manageable for design and development? | [5 empty] | 12.h
| T&E, logistics, training, software, HSI, EVM, PQM, technology, risk, programmatic, interoperability | i. Is the program schedule executable within the anticipated cost and technical risks? | [5 empty] | 12.i
| T&E, logistics, training, software, HSI, EVM, PQM, technology, risk, programmatic, interoperability | j. Is the program properly staffed? | [5 empty] | 12.j
| programmatic | k. Is the program Non-Recurring Engineering (NRE) executable within the existing budget? | [5 empty] | 12.k
| T&E, software, logistics, HSI, programmatic | l. Is the preliminary CARD consistent with the approved system specification? | [5 empty] | 12.l
| programmatic, software | m. Is the software functionality in the system specification consistent with the software sizing estimates and resource loaded schedule? | [5 empty] | 12.m
| risk, technology, programmatic | n. Did the Technology Development (TD) work effort sufficiently reduce development risks? | [5 empty] | 12.n
| programmatic, technology | o. Does the status of the technical effort indicate contract compliance? | [5 empty] | 12.o
| T&E, logistics, training, software, HSI, EVM, PQM, technology, risk, programmatic, interoperability | p. Are there significant issues outside the scope of the contract? | [5 empty] | 12.p
| HSI, logistics, programmatic | q. Are logistics metrics identified in the APB? | [5 empty] | 12.q
| HSI, logistics, programmatic | r. Has the Ao portion of the APB been defined or updated for this phase of the program? | [5 empty] | 12.r
| T&E, HSI, logistics, programmatic | s. Has the Ao related portion of exit criteria (in terms of CAIV objectives)? | [5 empty] | 12.s
| T&E, HSI, logistics, programmatic | t. Is there any way to make Ao analysis more accurate for this program at this time? | [5 empty] | 12.t
| T&E, HSI, logistics, programmatic | u. Have other program planning documents been updated to include Ao related information appropriate for this phase, and what are they? | [5 empty] | 12.u
CAUTION: Entries, changes, deletions or comments should only be made on the checklist. Any entries entered directly on the summary pages will not be recorded within the checklist and will disable linkage between the checklist and the summary pages.
Question
Flagged
High Priority
HSI
Interoperability
Logistics
Training
PQM
Programmatic
Risk
Software
T&E
Technology
Show All
Hide TD
Unhide TD
Unhide NA
Hide NA
Level 1
EVM

## Red
“Systems Engineering for Mission Success”
|  | System Requirements Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigation

## Yellow
“Systems Engineering for Mission Success”
|  | System Requirements Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigation

## Unknown
“Systems Engineering for Mission Success”
|  | System Requirements Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigation

## NA
“Systems Engineering for Mission Success”
|  | System Requirements Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigation

## Level 1
“Systems Engineering for Mission Success”
|  | System Requirements Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigation
0 | Level 1, logistics, programmatic, software, risk, PQM, EVM, T&E, HSI, training, technology, interoperability | 1. Timing / Entry Criteria | 0 | 0 | 0 | 0 | 0 | 1 | 0
0 | Level 1, logistics, programmatic, software, risk, PQM, EVM, T&E, HSI, training, technology, interoperability | 2. Planning | 0 | 0 | 0 | 0 | 0 | 2 | 0
0 | Level 1, T&E, logistics, PQM, HSI, training, risk, software, EVM, technology, programmatic, interoperability | 3. Program schedule | 0 | 0 | 0 | 0 | 0 | 3 | 0
0 | Level 1, T&E, logistics, PQM, HSI, training, risk, software, EVM, technology, programmatic, interoperability | 4. Management Metrics | 0 | 0 | 0 | 0 | 0 | 4 | 0
0 | Level 1, software, logistics, risk, HSI, PQM, T&E, technology, EVM, training, programmatic, interoperability | 5. Program Staffing | 0 | 0 | 0 | 0 | 0 | 5 | 0
0 | Level 1, logistics, PQM, T&E, software, risk, EVM, training, programmatic, interoperability, HSI, technology | 6. Process Review | 0 | 0 | 0 | 0 | 0 | 6 | 0
0 | Level 1, software, T&E, EVM, logistics, risk, PQM, training, programmatic, HSI, technology, interoperability | 7. Product Support | 0 | 0 | 0 | 0 | 0 | 7 | 0
0 | level 1, training, HSI, technology, risk, PQM, T&E, logistics, software, interoperability, programmatic | 8. System Requirements | 0 | 0 | 0 | 0 | 0 | 8 | 0
0 | Level 1, T&E, software, HSI, logistics, risk, programmatic, interoperability | 9. Technology Development | 0 | 0 | 0 | 0 | 0 | 9 | 0
0 | Level 1, software, T&E, logistics, EVM, training, risk, PQM, HSI, technology, programmatic, interoperability | 10. System Verification | 0 | 0 | 0 | 0 | 0 | 10 | 0
0 | Level 1, T&E, logistics, PQM, HSI, training, risk, software, EVM, technology, programmatic, interoperability | 11. Program Risk Assessment | 0 | 0 | 0 | 0 | 0 | 11 | 0
0 | Level 1, T&E, logistics, PQM, HSI, training, risk, software, EVM, technology, programmatic, interoperability | 12. Completion / Exit Criteria | 0 | 0 | 0 | 0 | 0 | 12 | 0
|  | Total: | 0 | 0 | 0 | 0 | 0
Return to SRR